## MADINAH Migration Plan (hidden)
MADINAH Migration Flow | Activity | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Remark
| Database Migration (1st Round) (20-May-26) | [7 empty] | Madinah Database Migration (1st Round) completed
| SLD 1st patch (10 SS) | [7 empty] | SLD 1st patch in Madinah: (to be confirmed by CET)
| Validation by SE | [7 empty] | 3 days FF with SLD 1st patch
| E2E for 1st patch (10 SS - 20 points) | [7 empty] | Start 18-Jun Finish: 21-Jun Depend on Telecom Readiness
| SLD 2nd patch | [7 empty] | Start: 23-May Finish: 30-May
| SLD 3rd patch | [7 empty] | Start: 01-Jun Finish: 08-Jun
| SLD 4th patch | [7 empty] | Start: 01-Jun Finish: 08-Jun
| SLD 5th patch | [7 empty] | Start: 01-Jun Finish: 08-Jun
| SLD 6th patch | [7 empty] | Start: 09-Jun Finish: 16-Jun
| SLD 7th patch | [7 empty] | Start: 09-Jun Finish: 16-Jun
| SLD 8th patch | [7 empty] | Start: 09-Jun Finish: 16-Jun
| SLD 9th patch | [7 empty] | Start: 17-Jun Finish: 24-Jun
| SLD 10th patch | [7 empty] | Start: 24-Jul Finish: 30-Jul
| Final Validation by SE | [7 empty] | Start: 01-Aug Finish: 07-Aug E2E test shall be Finish to Finish +3 days with SLD
| Completion of E2E test | [7 empty] | shall be by mid of Aug-2026 (for Madinah)
| Alarm & Reporting Migration (14-Jun-26) | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability
| UI & Display Configuration (14-Jun-26) | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability
| Historian Migration (15-Aug-26) | [7 empty] | Depend on : *1st Round of Database Migration *Data Structure & Analysis from SE
| ADMS SAT | [7 empty] | Depend on : *Migration completion *80% of E2E testing
| Hardware cybersecurity test | [7 empty] | 3 days
| Functional test | [7 empty] | 5 days
| Performance test | [7 empty] | 3 days
| Integration test | [7 empty] | 2 days
| Redundancy test | [7 empty] | 2 days
| Stability & unstructure test | [7 empty] | 1 day
| Regression test | [7 empty] | 1 day
Training inside KSA
Training in China
| DERMS Software Installation shall start by 19-May-26 (Madinah) | [7 empty] | OT switches shall be mobilized by 16-May
DERMS SAT
Contract. TCC: 24-Jul-26
Variance:
- 6 Weeks

## Progress Summary (hidden)
0% | Not Strated | Not Strated | SDCC - Overall Upstream Progress
50% | In Progress | In Progress
100% | Completed | Completed
MADINAH Upstream Progress | [7 empty] | JEDDAH Upstream Progress | [7 empty] | MAKKAH Upstream Progress
Batch No. | Planned % | Completed % | SLD Submission | SLD Validation | E2E for Grid SS | E2E Rectification | Cutover | Batch No. | Planned % | Completed % | SLD Submission | SLD Validation | E2E for Grid SS | E2E Rectification | Cutover | Batch No. | Planned % | Completed % | SLD Submission | SLD Validation | E2E for Grid SS | E2E Rectification | Cutover | -
Batch 01 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 01 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 01 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 02 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 02 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 02 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 03 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 03 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 03 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 04 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 04 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 04 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 05 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 05 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 05 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 06 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 06 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 06 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 07 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 07 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 07 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 08 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 08 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 08 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 09 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 09 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 09 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 10 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 10 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 10 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ABHA Upstream Progress | [15 empty] | JIZAN Upstream Progress
Batch No. | Planned % | Completed % | SLD Submission | SLD Validation | E2E for Grid SS | E2E Rectification | Cutover | [8 empty] | Batch No. | Planned % | Completed % | SLD Submission | SLD Validation | E2E for Grid SS | E2E Rectification | Cutover
Batch 01 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 01 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 02 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 02 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 03 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 03 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 04 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 04 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 05 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 05 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 06 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 06 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 07 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 07 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 08 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 08 | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Summary Dates (hidden)
MADINAH | [5 empty] | ABHA
|  | % Progress | Planned Finish | Expected Finish | Variance |  |  | % Progress | Planned Finish | Expected Finish | Variance
Upstream | SLD & DB Submission & Validation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Upstream | SLD & DB Submission & Validation | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| E2E Test | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | E2E Test | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| SAT | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | SAT | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Final Cuttover - Live on | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | Final Cuttover - Live on | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Downstream | SLD & DB Submission & Validation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Downstream | SLD & DB Submission & Validation | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| E2E Test | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | E2E Test | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| SAT | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | SAT | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Final Cuttover - Live on | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | Final Cuttover - Live on | #VALUE! | #VALUE! | #VALUE! | #VALUE!
JEDDAH | [5 empty] | JIZAN
|  | % Progress | Planned Finish | Expected Finish | Variance |  |  | % Progress | Planned Finish | Expected Finish | Variance
Upstream | SLD & DB Submission & Validation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Upstream | SLD & DB Submission & Validation | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| E2E Test | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | E2E Test | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| SAT | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | SAT | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Final Cuttover - Live on | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | Final Cuttover - Live on | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Downstream | SLD & DB Submission & Validation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Downstream | SLD & DB Submission & Validation | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| E2E Test | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | E2E Test | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| SAT | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | SAT | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Final Cuttover - Live on | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | Final Cuttover - Live on | #VALUE! | #VALUE! | #VALUE! | #VALUE!
MAKKAH
|  | % Progress | Planned Finish | Expected Finish | Variance
Upstream | SLD & DB Submission & Validation | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| E2E Test | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| SAT | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Final Cuttover - Live on | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Downstream | SLD & DB Submission & Validation | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| E2E Test | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| SAT | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Final Cuttover | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## ABHA Migration Plan
| Workstream | Activity | Working Days | Planned Start | Planned Finish | Expected Start | Expected Finish | Actual Start / Expected Start | Actual Finish / Expected Finish | % Progress | Status | Root Cuase of Delay | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Remark | Planned Manpower | Actual Manpower | Resource Type | RESOURCE ALLOCATION | PRODUCTIVITY MATRIX
|  | Database Migration (1st Round) |  |  | Completed |  | Completed |  |  | 100% | Completed | [8 empty] | Abha Database Migration (1st Round) completed
1st Batch (6 SS) | Upstream | SLD and DB - Upstream | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 100% | Completed | [14 empty] | 6 Days Calendar | SLD Submission | Batch 01 | 2026-05-24
| Upstream | Validation by SE - Upstream | 42 | 2026-05-12 | 2026-07-05 | 2026-05-12 | 2026-07-05 | 2026-05-12 | 2026-07-05 | 100% | Completed | [14 empty] | 6 Days Calendar | SLD Validation | Batch 01 | 2026-05-25
| Upstream | Telecom Rediness - Upstream |  | Started | 2026-07-30 | Started | 2026-08-11 | started |  | 71% | In Progress | Abha delayed due to "Bisha LDC pretest" not started and the E1 TSRs still not recieved. | [7 empty] | *(DVM-E1-TSR ) should be received no later than 16-Jul-26 *Bisha LDC DC Issue should be solved | [8 empty] | 2026-05-26
| Upstream | E2E - Upstream | 2 | 2026-08-02 | 2026-08-03 | 2026-08-12 | 2026-08-13 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 1 |  |  | Leader - 1 (Liang shifei) | 3SS/DAY | 5 Days Calendar | E2E for Grid SS | Batch 01 | 2026-05-27
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-04 | 2026-08-05 | 2026-08-16 | 2026-08-17 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 |  |  |  |  | 5 Days Calendar | E2E Rectification | Batch 01 | 2026-05-28
2026-09-23
2nd Batch (10 SS) | Upstream | SLD and DB - Upstream | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 100% | Completed | [15 empty] | SLD Submission | Batch 02 | 2026-09-23
| Upstream | Validation by SE - Upstream | 13 | 2026-06-21 | 2026-07-05 | 2026-06-21 | 2026-07-05 | 2026-06-21 | 2026-07-05 | 100% | Completed | [8 empty] | Batch 02 Validated from Control Systema Division Team ans waiting final signedSLD & DB Approval Form | [6 empty] | SLD Validation | Batch 02
| Upstream | E2E - Upstream | 4 | 2026-08-04 | 2026-08-09 | 2026-08-15 | 2026-08-18 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 1 |  |  | Leader - 1 (Liang shifei) | 3SS/DAY |  | E2E for Grid SS | Batch 02
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-10 | 2026-08-11 | 2026-08-19 | 2026-08-20 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 02
3rd Batch (14 SS) | Upstream | SLD and DB - Upstream | 7 | 2026-07-06 | 2026-07-13 | 2026-07-06 | 2026-07-13 | 2026-07-06 | 2026-07-13 | 100% | Completed | [15 empty] | SLD Submission | Batch 03
| Upstream | Validation by SE - Upstream | 3 | 2026-07-14 | 2026-07-16 | 2026-07-14 | 2026-07-16 | 2026-07-14 | 2026-07-16 | 100% | Completed | [8 empty] | waiting for signs | [6 empty] | SLD Validation | Batch 03
| Upstream | E2E - Upstream | 5 | 2026-08-10 | 2026-08-16 | 2026-08-19 | 2026-08-25 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 1 |  |  | Leader - 1 (Liang shifei) | 3SS/DAY |  | E2E for Grid SS | Batch 03
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-17 | 2026-08-18 | 2026-08-26 | 2026-08-27 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 03
4th Batch (16 SS) | Upstream | SLD and DB - Upstream | 6 | 2026-07-18 | 2026-07-23 | 2026-07-18 | 2026-07-23 | 2026-07-14 | 2026-07-18 | 100% | Completed | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2 (Chen lei, Wang boyang) TOTAL SUPPORT DRAFTMAN -1 (Meshari) | 3/DAY APPROX |  | SLD Submission | Batch 04
| Upstream | Validation by SE - Upstream | 3 | 2026-07-25 | 2026-07-27 | 2026-07-25 | 2026-07-27 | 2026-07-18 | 2026-07-22 | 100% | Completed | [9 empty] | 3 | [5 empty] | SLD Validation | Batch 04
| Upstream | E2E - Upstream | 6 | 2026-08-17 | 2026-08-24 | 2026-08-26 | 2026-09-02 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 1 |  |  | Leader - 1 (Liang shifei) | 3SS/DAY |  | E2E for Grid SS | Batch 04
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-25 | 2026-08-26 | 2026-09-03 | 2026-09-06 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 04
5th Batch (16 SS) | Upstream | SLD and DB - Upstream | 6 | 2026-07-28 | 2026-08-03 | 2026-07-28 | 2026-08-03 | 2026-07-18 | 2026-07-23 | 100% | Completed | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2 (Chen lei, Wang boyang) TOTAL SUPPORT DRAFTMAN -1 (Meshari) | 3/DAY(SS) |  | SLD Submission | Batch 05
| Upstream | Validation by SE - Upstream | 3 | 2026-08-04 | 2026-08-06 | 2026-08-04 | 2026-08-06 | 2026-07-25 |  | 10% | In Progress | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 05
| Upstream | E2E - Upstream | 6 | 2026-08-25 | 2026-09-01 | 2026-09-03 | 2026-09-10 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 1 |  |  | Leader - 1 (Liang shifei) | 3SS/DAY |  | E2E for Grid SS | Batch 05
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-02 | 2026-09-03 | 2026-09-13 | 2026-09-14 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 05
6th Batch (14 SS) | Upstream | SLD and DB - Upstream | 6 | 2026-08-08 | 2026-08-13 | 2026-08-08 | 2026-08-13 |  |  |  | Not Started | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2 (Chen lei, Wang boyang) TOTAL SUPPORT DRAFTMAN -1 (Meshari) | 3/DAY(SS) |  | SLD Submission | Batch 06
| Upstream | Validation by SE - Upstream | 3 | 2026-08-15 | 2026-08-17 | 2026-08-15 | 2026-08-17 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 06
| Upstream | E2E - Upstream | 5 | 2026-09-02 | 2026-09-08 | 2026-09-12 | 2026-09-16 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 1 |  |  | Leader - 1 (Liang shifei) | 3SS/DAY |  | E2E for Grid SS | Batch 06
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-09 | 2026-09-10 | 2026-09-17 | 2026-09-20 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 06
7th Batch (15 SS) | Upstream | SLD and DB - Upstream | 6 | 2026-08-18 | 2026-08-24 | 2026-08-18 | 2026-08-24 |  |  |  | Not Started | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2 (Chen lei, Wang boyang) TOTAL SUPPORT DRAFTMAN -1 (Meshari) | 3/DAY(SS) |  | SLD Submission | Batch 07
| Upstream | Validation by SE - Upstream | 3 | 2026-08-25 | 2026-08-27 | 2026-08-25 | 2026-08-27 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 07
| Upstream | E2E - Upstream | 5 | 2026-09-09 | 2026-09-15 | 2026-09-17 | 2026-09-24 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 1 |  |  | Leader - 1 (Liang shifei) | 3SS/DAY |  | E2E for Grid SS | Batch 07
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-16 | 2026-09-17 | 2026-09-27 | 2026-09-28 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 07
8th Batch (15 SS) | Upstream | SLD and DB - Upstream | 6 | 2026-08-29 | 2026-09-03 | 2026-08-29 | 2026-09-03 |  |  |  | Not Started | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2 (Chen lei, Wang boyang) TOTAL SUPPORT DRAFTMAN -1 (Meshari) | 3/DAY(SS) |  | SLD Submission | Batch 08
| Upstream | Validation by SE - Upstream | 3 | 2026-09-05 | 2026-09-07 | 2026-09-05 | 2026-09-07 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 08
| Upstream | E2E - Upstream | 5 | 2026-09-16 | 2026-09-22 | 2026-09-26 | 2026-09-30 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 1 |  |  | Leader - 1 (Liang shifei) | 3SS/DAY |  | E2E for Grid SS | Batch 08
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-24 | 2026-09-27 | 2026-10-01 | 2026-10-04 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 08
Migration | Migration | Alarm & Reporting Migration | 19 | 2026-08-18 | 2026-09-08 | 2026-08-23 | 2026-09-13 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration | 1 |  |  | Leader - 1(Waqar) |  | 6 Days Calendar
| Migration | UI & Display Configuration | 19 | 2026-07-27 | 2026-08-17 | 2026-08-01 | 2026-08-22 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration | 1 |  |  | Leader - 1(Waqar) |  | 6 Days Calendar
| Migration | Historian Migration | 66 | 2026-07-27 | 2026-10-11 | 2026-08-01 | 2026-10-15 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration *Data Structure & Analysis from SE | 1 |  |  | Leader - 1(Waqar) |  | 6 Days Calendar
Cut Over - Upstream (Live-On) | Live On - Upstream | Cut Over（Batch 1:8） | 2 | 2026-09-29 | 2026-09-30 | 2026-10-07 | 2026-10-08 |  |  |  | Not Started | [8 empty] | *Completed SAT | 1 |  |  | Leader - 1 (Liang shifei)
Training | Training | Training inside KSA | 30 | 2026-08-15 | 2026-09-27 | 2026-08-15 | 2026-09-27 |  |  |  | Not Started | [8 empty] | on Job training to be conducted on each SDCC | 1 |  |  | Leader - 1(Waqar) |  | 5 Days Calendar
| Training | Training in Factory | 30 | 2026-11-01 | 2026-12-10 | 2026-11-09 | 2026-12-20 |  |  |  | Not Started | [8 empty] | After the cutover of all five-sites | 1 |  |  |  |  | 5 Days Calendar
DERMS | DERMS | DERMS Software Installation | 31 | 2026-07-08 | 2026-08-12 | 2026-07-08 | 2026-08-12 |  |  | 25% | In Progress | [8 empty] | Firewall Configuration and required access rules shall be fully implemented and Verified. Network Access between relevant systems and sites shall be available and confirmed. Connection between DC & DR shall be completed to support DC/DR communication and failover test. All required ports, routing rules and security policies shall be provided before testing. Server Certificates shall be issued by SE. | 1
| DERMS | DERMS SAT | 16 | 2026-09-02 | 2026-09-23 | 2026-09-02 | 2026-09-23 |  |  |  | Not Started | [8 empty] | Finalization of Interfaces with SE IT/OT Systems. Availability of DER Data. | 1
DS(Batch 1) 6-GSS | Downstream | SLD and DB Validation Demo | 1 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 2026-07-12 |  |  | 100% | Completed | [9 empty] | 1
| Downstream | SLD and DB(Feeders of GSS Batch1) Feeders 70 (Graphic,Database,Link) | 6 | 2026-07-19 | 2026-07-25 | 2026-07-19 | 2026-07-29 | 2026-07-19 | 2026-07-29 | 30% | Delayed | control center share new updates for all feeders | [7 empty] | Draft Man will mobilize on 7-Jul-26 | 2 |  |  | Total Expereienced Draftsmans - 1(Duan zheng) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 12/DAY
| Downstream | SLD and DB Validation | 4 | 2026-07-26 | 2026-07-29 | 2026-07-30 | 2026-08-03 | 2026-07-21 |  | 5% | In Progress | [9 empty] | 1
DS(Batch 2) 10 -GSS | Downstream | SLD and DB(Feeders of GSS Batch2) Feeders 110 (Graphic,Database,Link) | 4 | 2026-07-26 | 2026-07-29 | 2026-07-30 | 2026-08-03 | 2026-07-30 |  |  | Delayed | delay in 1st batch submission | [7 empty] | Draft Man will mobilize on 7-Jul-26 | 2 |  |  | Total Expereienced Draftsmans - 1(Duan zheng) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 28/DAY
| Downstream | SLD and DB Validation | 5 | 2026-07-30 | 2026-08-04 | 2026-08-04 | 2026-08-09 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 3) 14-GSS | Downstream | SLD and DB(Feeders of GSS Batch3) Feeders 140 (Graphic,Database,Link) | 5 | 2026-07-30 | 2026-08-04 | 2026-08-04 | 2026-08-09 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Duan zheng) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 28/DAY
| Downstream | SLD and DB Validation | 5 | 2026-08-05 | 2026-08-10 | 2026-08-10 | 2026-08-15 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 4) 16-GSS | Downstream | SLD and DB(Feeders of GSS Batch4) Feeders 160 (Graphic,Database,Link) | 5 | 2026-08-05 | 2026-08-10 | 2026-08-10 | 2026-08-15 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Duan zheng) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 32/DAY
| Downstream | SLD and DB Validation | 5 | 2026-08-11 | 2026-08-16 | 2026-08-16 | 2026-08-20 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 5) 16-GSS | Downstream | SLD and DB(Feeders of GSS Batch5) Feeders 170 (Graphic,Database,Link) | 5 | 2026-08-11 | 2026-08-16 | 2026-08-16 | 2026-08-20 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Duan zheng) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 34/DAY
| Downstream | SLD and DB Validation | 5 | 2026-08-17 | 2026-08-22 | 2026-08-22 | 2026-08-26 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 6) 14-GSS | Downstream | SLD and DB(Feeders of GSS Batch6) Feeders 150 (Graphic,Database,Link) | 4 | 2026-08-17 | 2026-08-20 | 2026-08-22 | 2026-08-25 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Duan zheng) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 38/DAY
| Downstream | SLD and DB Validation | 4 | 2026-08-22 | 2026-08-25 | 2026-08-26 | 2026-08-30 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 7) 15-GSS | Downstream | SLD and DB(Feeders of GSS Batch7) Feeders 160 (Graphic,Database,Link) | 4 | 2026-08-22 | 2026-08-25 | 2026-08-26 | 2026-08-30 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Duan zheng) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 40/DAY
| Downstream | SLD and DB Validation | 4 | 2026-08-26 | 2026-08-30 | 2026-08-31 | 2026-09-03 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 8) 15-GSS | Downstream | SLD and DB(Feeders of GSS Batch8) Feeders 150 (Graphic,Database,Link) | 4 | 2026-08-26 | 2026-08-30 | 2026-08-31 | 2026-09-03 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Duan zheng) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 38/DAY
| Downstream | SLD and DB Validation | 4 | 2026-08-31 | 2026-09-03 | 2026-09-05 | 2026-09-08 |  |  |  | Not Started | [9 empty] | 1
DS(E2E) | Downstream | E2E for SFD (Total 7949 8% For Testing 636) | 33 | 2026-07-30 | 2026-09-14 | 2026-08-04 | 2026-09-17 |  |  |  | Not Started | [8 empty] | Depend on STC TELECOME CIRCUITS READINESS(INSTALLATION, HARDWARE, SOFTWARE, CONFIGURATION, TRAFFIC, REROUTING,....ETC) Depend on Availability of SE Field Engineer Start the E2E test after the approval for the first downstream batch E2E RMU Rate = 29/ Day | 3 |  |  | Leader - 1 (Chen zheng) Support - 2 (He fei) | 29/DAY | 6 Days Calendar
CUTOVER | Live On - Downstream | Cuttover | 2 | 2026-09-29 | 2026-09-30 | 2026-10-07 | 2026-10-08 |  |  |  | Not Started | [8 empty] | After STC Success E2E | 1 |  |  | Leader - 1 (Chen zheng) Support - 2 (He fei) |  | 5 Days Calendar
ADMS SAT | ADMS SAT | Hardware cybersecurity test | 2 | 2026-09-13 | 2026-09-14 | 2026-09-21 | 2026-09-22 |  |  |  | Not Started | [9 empty] | 1 |  |  | Team - 3 (Wang boyang, Duan zheng, He fei) Support -1 (Meshari)
| ADMS SAT | Functional test - ADMS | 4 | 2026-09-15 | 2026-09-20 | 2026-09-23 | 2026-09-28 |  |  |  | Not Started | [9 empty] | 1
| ADMS SAT | Integration test | 4 | 2026-09-15 | 2026-09-20 | 2026-09-23 | 2026-09-28 |  |  |  | Not Started | [8 empty] | ADMS Integration Testing is dependent on the successful completion of all Phase 1 interface tests for the Centralized ESB. In accordance with the Local ESB schedule, the related integration preparation and coordination activities shall commence at least 45 days in advance. | 1
| ADMS SAT | Redundancy test | 2 | 2026-09-21 | 2026-09-22 | 2026-09-29 | 2026-09-30 |  |  |  | Not Started | [9 empty] | 1
| ADMS SAT | Stability | 2 | 2026-09-23 | 2026-09-26 | 2026-10-01 | 2026-10-04 |  |  |  | Not Started | [9 empty] | 1
| ADMS SAT | Regression test &unstructure test | 1 | 2026-09-27 | 2026-09-27 | 2026-10-05 | 2026-10-05 |  |  |  | Not Started | [9 empty] | 1
| ADMS SAT | Performance test | 1 | 2026-09-28 | 2026-09-28 | 2026-10-06 | 2026-10-06 |  |  |  | Not Started | [9 empty] | 1
Cyber Audit | Training | Cyber Audit Phase1 | 16 | 2026-08-20 | 2026-09-10 | 2026-08-30 | 2026-09-20 |  |  |  | Not Started | [8 empty] | Cutover 1.Depend on the Approval for DTS-628 2.Depend on the telecom readiness | 1
| Training | Cyber Audit Phase2 | 20 | 2026-12-10 | 2027-01-06 | 2026-12-10 | 2027-01-06 |  |  |  | Not Started | [8 empty] | 1.Centralized Cybersecurity Audit 2.Depend on the SDCCs telecom readiness | 1
Integration | Integration | DNMC Integration | 21 | 2026-09-07 | 2026-09-30 | 2026-09-07 | 2026-09-30 |  |  |  | Not Started | [8 empty] | 1.Depend on DNMC System Completed before 10 Aug, 2026 2.DNMC datapoint Scope to be confirmed by max 10, Aug 2026 3.DNMC <-----> DCC telecom completed by max 31 Aug, 2026 4.ICCP Configuration finished by 10 Aug, 2026 5.Testing（SDCC & DNMC ICCP Channel Testing,）finished by 20 Aug, 2026 | 1
| Integration | Local ESB software Installation | 9 | 2026-07-12 | 2026-07-21 | 2026-07-12 | 2026-07-21 |  |  | 100% | Completed | [8 empty] | SOFTWARE INSTALLATION | 1
| Integration | DC-DR SYNC | 37 | 2026-10-15 | 2026-11-26 | 2026-10-15 | 2026-11-26 |  |  |  | Not Started | [8 empty] | Depend on availibility of LAN/WAN, to be10 - 12 weeks from design approval * TEMPRORY CONNECTION BETWEEN OT FW. TO MPLS CAN BE DONE TO ACHIVE THE SYCRONIZATION BETWEEN DC & DR | 1
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26

## Jizan Migration Plan
A
|  | Workstream | Activity | Working Days | Planned Start | Planned Finish | Expected Start | Expected Finish | Actual Start / Expected Start | Actual Finish / Expected Finish | % Progress | Status | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Root Cuase of Delay | Remark | Planned Manpower | Actual Manpower | Resource Type | RESOURCE ALLOCATION | PRODUCTIVITY MATRIX | 7 Days Claendar
|  |  | Database Migration (1st Round) (20-May-26) | [7 empty] | 100% | #REF! | [8 empty] | Jizan Database Migration (1st Round) completed | [5 empty] | 6 Days Calendar
| 1st Batch (7 SS) | Upstream | SLD and DB - Upstream | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 100% | Completed | [14 empty] | 5 Days Calendar | SLD Submission | Batch 01 | 46166
|  | Upstream | Validation by SE - Upstream | 38 | 2026-05-17 | 2026-07-05 | 2026-05-17 | 2026-07-05 | 2026-05-17 | 2026-07-05 | 100% | Completed | [15 empty] | SLD Validation | Batch 01 | 46167
|  | Upstream | Telecom Rediness - Upstream |  | Started | 2026-07-26 | Started | 2026-07-26 |  |  | 94% | In Progress | [8 empty] | *(DVM-E1-TSR ) should be received no later than 16-Jul-26 | [8 empty] | 46168
|  | Upstream | E2E - Upstream | 3 | 2026-07-27 | 2026-07-29 | 2026-07-27 | 2026-07-29 |  |  |  | Not Started | [8 empty] | Grid Substation Depend on Telecom Readiness (29-Jul-26) Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Wang xiaozui) | 3SS/DAY |  | E2E for Grid SS | Batch 01 | 46169
|  | Upstream | E2E Comments Rectification - Upstream | 2 | 2026-07-30 | 2026-08-02 | 2026-07-30 | 2026-08-02 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 01 | 46170
|  |  | - Upstream | [26 empty] | 46288
| 2nd Batch (6 SS) | Upstream | SLD and DB - Upstream | 1 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 2026-06-11 | 100% | Completed | [15 empty] | SLD Submission | Batch 02 | 46288
|  | Upstream | Validation by SE - Upstream | 20 | 2026-06-13 | 2026-07-05 | 2026-06-13 | 2026-07-05 | 2026-06-13 | 2026-07-05 | 100% | Completed | [15 empty] | SLD Validation | Batch 02
|  | Upstream | E2E - Upstream | 2 | 2026-07-30 | 2026-08-02 | 2026-07-30 | 2026-08-02 |  |  |  | Not Started | [9 empty] | 1 |  |  | Leader - 1 (Wang xiaozui) | 3SS/DAY |  | E2E for Grid SS | Batch 02
|  | Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-03 | 2026-08-04 | 2026-08-03 | 2026-08-04 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | E2E Rectification | Batch 02
- Upstream
| 3rd Batch (14 SS) | Upstream | SLD and DB - Upstream | 16 | 2026-06-17 | 2026-07-05 | 2026-06-17 | 2026-07-05 | 2026-06-17 | 2026-07-05 | 100% | Completed | [15 empty] | SLD Submission | Batch 03
|  | Upstream | Validation by SE - Upstream | 3 | 2026-07-06 | 2026-07-08 | 2026-07-06 | 2026-07-08 | 2026-07-06 | 2026-07-08 | 100% | Completed | [15 empty] | SLD Validation | Batch 03
|  | Upstream | E2E - Upstream | 5 | 2026-08-03 | 2026-08-09 | 2026-08-03 | 2026-08-09 |  |  |  | Not Started | [9 empty] | 1 |  |  | Leader - 1 (Wang xiaozui) | 3SS/DAY |  | E2E for Grid SS | Batch 03
|  | Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-10 | 2026-08-11 | 2026-08-10 | 2026-08-11 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | E2E Rectification | Batch 03
- Upstream
| 4th Batch (11 SS) | Upstream | SLD and DB - Upstream | 7 | 2026-07-09 | 2026-07-16 | 2026-07-09 | 2026-07-16 | 2026-07-09 | 2026-07-13 | 100% | Completed | [15 empty] | SLD Submission | Batch 04
|  | Upstream | Validation by SE - Upstream | 3 | 2026-07-18 | 2026-07-20 | 2026-07-18 | 2026-07-20 | 2026-07-14 | 2026-07-14 | 100% | Completed | [8 empty] | WAITING FOR SIGN | [6 empty] | SLD Validation | Batch 04
|  | Upstream | E2E - Upstream | 5 | 2026-08-10 | 2026-08-16 | 2026-08-10 | 2026-08-16 |  |  |  | Not Started | [9 empty] | 1 |  |  | Leader - 1 (Wang xiaozui) | 3SS/DAY |  | E2E for Grid SS | Batch 04
|  | Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-17 | 2026-08-18 | 2026-08-17 | 2026-08-18 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | E2E Rectification | Batch 04
- Upstream
| 5th Batch (11 SS) | Upstream | SLD and DB - Upstream | 7 | 2026-07-21 | 2026-07-28 | 2026-07-21 | 2026-07-28 | 2026-07-15 | 2026-07-16 | 100% | Completed | [8 empty] | UNDER REVIEW WITH SITE SE TEAM BEFORE OFFICIL SUBMISSION | 2 |  |  | Total Expereienced Draftsmans - 1 (Han zijian) TOTAL SUPPORT DRAFTMAN -1 (Daka) | 2/DAY(SS) |  | SLD Submission | Batch 05
|  | Upstream | Validation by SE - Upstream | 3 | 2026-07-29 | 2026-08-01 | 2026-07-29 | 2026-08-01 | 2026-07-18 | 2026-07-20 | 100% | Completed | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 05
|  | Upstream | E2E - Upstream | 4 | 2026-08-17 | 2026-08-20 | 2026-08-17 | 2026-08-20 |  |  |  | Not Started | [9 empty] | 1 |  |  | Leader - 1 (Wang xiaozui) | 3SS/DAY |  | E2E for Grid SS | Batch 05
|  | Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-23 | 2026-08-24 | 2026-08-23 | 2026-08-24 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | E2E Rectification | Batch 05
- Upstream
| 6th Batch (11 SS) | Upstream | SLD and DB - Upstream | 7 | 2026-08-02 | 2026-08-09 | 2026-08-02 | 2026-08-09 | 2026-07-18 | 2026-07-21 | 100% | Completed | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Han zijian) TOTAL SUPPORT DRAFTMAN -1 (Daka) | 2/DAY(SS) |  | SLD Submission | Batch 06
|  | Upstream | Validation by SE - Upstream | 3 | 2026-08-10 | 2026-08-12 | 2026-08-10 | 2026-08-12 | 2026-07-22 | 2026-07-22 | 100% | Completed | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 06
|  | Upstream | E2E - Upstream | 3 | 2026-08-22 | 2026-08-25 | 2026-08-22 | 2026-08-25 |  |  |  | Not Started | [9 empty] | 1 |  |  | Leader - 1 (Wang xiaozui) | 4SS/DAY |  | E2E for Grid SS | Batch 06
|  | Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-26 | 2026-08-27 | 2026-08-26 | 2026-08-27 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | E2E Rectification | Batch 06
- Upstream
| 7th Batch (12 SS) | Upstream | SLD and DB - Upstream | 7 | 2026-08-13 | 2026-08-20 | 2026-08-13 | 2026-08-20 | 2026-07-21 |  | 75% | In Progress | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Han zijian) TOTAL SUPPORT DRAFTMAN -1 (Daka) | 2/DAY(SS) |  | SLD Submission | Batch 07
|  | Upstream | Validation by SE - Upstream | 3 | 2026-08-22 | 2026-08-24 | 2026-08-22 | 2026-08-24 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 07
|  | Upstream | E2E - Upstream | 4 | 2026-08-26 | 2026-08-31 | 2026-08-26 | 2026-08-31 |  |  |  | Not Started | [9 empty] | 1 |  |  | Leader - 1 (Wang xiaozui) | 3SS/DAY |  | E2E for Grid SS | Batch 07
|  | Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-01 | 2026-09-02 | 2026-09-01 | 2026-09-02 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | E2E Rectification | Batch 07
- Upstream
| 8th Batch (13 SS) | Upstream | SLD and DB - Upstream | 7 | 2026-08-25 | 2026-09-01 | 2026-08-25 | 2026-09-01 | 2026-07-22 |  | 60% | In Progress | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Han zijian) TOTAL SUPPORT DRAFTMAN -1 (Daka) | 2/DAY(SS) |  | SLD Submission | Batch 08
|  | Upstream | Validation by SE - Upstream | 3 | 2026-09-02 | 2026-09-05 | 2026-09-02 | 2026-09-05 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 08
|  | Upstream | E2E - Upstream | 6 | 2026-09-06 | 2026-09-13 | 2026-09-06 | 2026-09-13 |  |  |  | Not Started | [9 empty] | 1 |  |  | Leader - 1 (Wang xiaozui) | 3SS/DAY |  | E2E for Grid SS | Batch 08
|  | Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-14 | 2026-09-15 | 2026-09-14 | 2026-09-15 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | E2E Rectification | Batch 08
| Migration | Migration | Alarm & Reporting Migration | 19 | 2026-08-16 | 2026-09-06 | 2026-08-16 | 2026-09-06 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration | 1 |  |  | Leader - 1(Sun mingming)
|  | Migration | UI & Display Configuration | 19 | 2026-08-12 | 2026-09-02 | 2026-08-12 | 2026-09-02 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration | 1 |  |  | Leader - 1(Sun mingming)
|  | Migration | Historian Migration | 66 | 2026-08-12 | 2026-10-27 | 2026-08-12 | 2026-10-27 |  |  |  | Not Started | [8 empty] | Depend on : *Data Structure & Analysis from SE | 1 |  |  | Leader - 1(Sun mingming)
| Cut Over - Upstream (Live-On) | Live On - Upstream | Cut Over（Batch1-8） | 3 | 2026-09-22 | 2026-09-24 | 2026-09-21 | 2026-09-23 |  |  |  | Not Started | [8 empty] | *Completed SAT | 1 |  |  | Leader - 1 (Wang xiaozui)
| Training | Training | Training inside KSA | 30 | 2026-08-10 | 2026-09-20 | 2026-08-10 | 2026-09-20 |  |  |  | Not Started | [9 empty] | 1 |  |  | Leader - 1(Sun mingming)
|  | Training | Training in Factory | 30 | 2026-10-29 | 2026-12-09 | 2026-10-28 | 2026-12-08 |  |  |  | Not Started | [8 empty] | After the cutover of all five-sites | 1
| DERMS | DERMS | DERMS Software Installation | 30 | 2026-07-29 | 2026-09-01 | 2026-07-29 | 2026-09-01 |  |  |  | Not Started | [8 empty] | Firewall Configuration and required access rules shall be fully implemented and Verified. Network Access between relevant systems and sites shall be available and confirmed. Connection between DC & DR shall be completed to support DC/DR communication and failover test. All required ports, routing rules and security policies shall be provided before testing. Server Certificates shall be issued by SE.
|  | DERMS | DERMS SAT | 15 | 2026-09-02 | 2026-09-23 | 2026-09-02 | 2026-09-23 |  |  |  | Not Started | [8 empty] | Finalization of Interfaces with SE IT/OT Systems. Availability of DER Data.
| DS(Batch 1) 7-GSS | Downstream | SLD and DB Validation Demo | 1 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 100% | Completed
|  | Downstream | SLD and DB(Feeders of GSS Batch1) Feeders 100 (Graphic,Database,Link) | 6 | 2026-07-21 | 2026-07-27 | 2026-07-21 | 2026-07-27 | 2026-07-22 |  | 15% | In Progress | [7 empty] | control center share new updates for all feeders |  | 2 |  |  | Total Expereienced Draftsmans - 1(Zhao xiaoyu) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 17/DAY
|  | Downstream | SLD and DB Validation | 4 | 2026-07-28 | 2026-08-01 | 2026-07-28 | 2026-08-01 |  |  |  | Not Started | [9 empty] | 1
| DS(Batch 2) 6 -GSS | Downstream | SLD and DB(Feeders of GSS Batch2) Feeders 150 (Graphic,Database,Link) | 5 | 2026-07-28 | 2026-08-02 | 2026-07-28 | 2026-08-02 |  |  |  | Not Started | [8 empty] | Draft Man will mobilize on 7-Jul-26 | 2 |  |  | Total Expereienced Draftsmans - 1(Zhao xiaoyu) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 30/DAY
|  | Downstream | SLD and DB Validation | 5 | 2026-08-03 | 2026-08-08 | 2026-08-03 | 2026-08-08 |  |  |  | Not Started | [9 empty] | 1
| DS(Batch 3) 14-GSS | Downstream | SLD and DB(Feeders of GSS Batch3) Feeders 160 (Graphic,Database,Link) | 5 | 2026-08-03 | 2026-08-08 | 2026-08-03 | 2026-08-08 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Zhao xiaoyu) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 32/DAY
|  | Downstream | SLD and DB Validation | 5 | 2026-08-09 | 2026-08-13 | 2026-08-09 | 2026-08-13 |  |  |  | Not Started | [9 empty] | 1
| DS(Batch 4) 11-GSS | Downstream | SLD and DB(Feeders of GSS Batch4) Feeders 160 (Graphic,Database,Link) | 5 | 2026-08-09 | 2026-08-13 | 2026-08-09 | 2026-08-13 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Zhao xiaoyu) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 32/DAY
|  | Downstream | SLD and DB Validation | 5 | 2026-08-15 | 2026-08-19 | 2026-08-15 | 2026-08-19 |  |  |  | Not Started | [9 empty] | 1
| DS(Batch 5) 11-GSS | Downstream | SLD and DB(Feeders of GSS Batch5) Feeders 160 (Graphic,Database,Link) | 5 | 2026-08-15 | 2026-08-19 | 2026-08-15 | 2026-08-19 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Zhao xiaoyu) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 32/DAY
|  | Downstream | SLD and DB Validation | 5 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-25 |  |  |  | Not Started | [9 empty] | 1
| DS(Batch 6) 11-GSS | Downstream | SLD and DB(Feeders of GSS Batch6) Feeders 160 (Graphic,Database,Link) | 5 | 2026-08-20 | 2026-08-25 | 2026-08-20 | 2026-08-25 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Zhao xiaoyu) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 32/DAY
|  | Downstream | SLD and DB Validation | 5 | 2026-08-26 | 2026-08-31 | 2026-08-26 | 2026-08-31 |  |  |  | Not Started | [9 empty] | 1
| DS(Batch 7) 12-GSS | Downstream | SLD and DB(Feeders of GSS Batch7) Feeders 160 (Graphic,Database,Link) | 5 | 2026-08-26 | 2026-08-31 | 2026-08-26 | 2026-08-31 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Zhao xiaoyu) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 32/DAY
|  | Downstream | SLD and DB Validation | 5 | 2026-09-01 | 2026-09-06 | 2026-09-01 | 2026-09-06 |  |  |  | Not Started | [9 empty] | 1
| DS(Batch 8) 13-GSS | Downstream | SLD and DB(Feeders of GSS Batch8) Feeders 160 (Graphic,Database,Link) | 5 | 2026-09-01 | 2026-09-06 | 2026-09-01 | 2026-09-06 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Zhao xiaoyu) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 32/DAY
|  | Downstream | SLD and DB Validation | 5 | 2026-09-07 | 2026-09-12 | 2026-09-07 | 2026-09-12 |  |  |  | Not Started | [9 empty] | 1
| DS(E2E) | Downstream | E2E for SFD (Total 6361 8% For Testing 508 ) | 31 | 2026-08-02 | 2026-09-13 | 2026-08-02 | 2026-09-13 |  |  |  | Not Started | [8 empty] | Depend on STC TELECOME CIRCUITS READINESS(INSTALLATION, HARDWARE, SOFTWARE, CONFIGURATION, TRAFFIC, REROUTING,....ETC) Depend on Availability of SE Field Engineer Start the E2E test after the approval for the first downstream batch. E2E RMU Rate = 17 / Day | 1 |  |  | Leader - 1 (Guo fei) | 17/DAY
| CUTOVER | Live On - Downstream | Cuttover | 1 | 2026-09-30 | 2026-09-30 | 2026-09-30 | 2026-09-30 |  |  |  | Not Started | [8 empty] | After STC Success E2E | 1 |  |  | Leader - 1 (Guo fei)
| ADMS SAT | ADMS SAT | Hardware cybersecurity test | 2 | 2026-09-14 | 2026-09-15 | 2026-09-14 | 2026-09-15 |  |  |  | Not Started | [9 empty] | 4 |  |  | Team - 3 (Zhao xiaoyu, Han zijian, Li Xuemei) Support -1 (Daka)
|  | ADMS SAT | Functional test - ADMS | 4 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 |  |  |  | Not Started | [9 empty] | 4
|  | ADMS SAT | Integration test | 4 | 2026-09-16 | 2026-09-21 | 2026-09-16 | 2026-09-21 |  |  |  | Not Started | [8 empty] | ADMS Integration Testing is dependent on the successful completion of all Phase 1 interface tests for the Centralized ESB. In accordance with the Local ESB schedule, the related integration preparation and coordination activities shall commence at least 45 days in advance. | 4
|  | ADMS SAT | Redundancy test | 2 | 2026-09-22 | 2026-09-23 | 2026-09-22 | 2026-09-23 |  |  |  | Not Started | [9 empty] | 4
|  | ADMS SAT | Stability | 2 | 2026-09-24 | 2026-09-27 | 2026-09-24 | 2026-09-27 |  |  |  | Not Started | [9 empty] | 4
|  | ADMS SAT | Regression test &unstructure test | 1 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 |  |  |  | Not Started | [9 empty] | 4
|  | ADMS SAT | Performance test | 1 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 |  |  |  | Not Started | [9 empty] | 4
| Cyber Audit | Cyber Audit | Cyber Audit Phase1 | 16 | 2026-08-23 | 2026-09-13 | 2026-08-23 | 2026-09-13 |  |  |  | Not Started | [8 empty] | Cutover 1.Depend on the Approval for DTS-628 2.Depend on the telecom readiness
|  | Cyber Audit | Cyber Audit Phase2 | 20 | 2026-12-10 | 2027-01-06 | 2026-12-10 | 2027-01-06 |  |  |  | Not Started | [8 empty] | 1.Centralized Cybersecurity Audit 2.Depend on the SDCCs telecom readiness
| Integration | Integration | DNMC Integration | 21 | 2026-09-06 | 2026-09-30 | 2026-09-06 | 2026-09-30 |  |  |  | Not Started | [8 empty] | 1.Depend on DNMC System Completed before 10 Aug, 2026 2.DNMC datapoint Scope to be confirmed by max 10, Aug 2026 3.DNMC <-----> DCC telecom completed by max 31 Aug, 2026 4.ICCP Configuration finished by 10 Aug, 2026 5.Testing（SDCC & DNMC ICCP Channel Testing,）finished by 20 Aug, 2026
|  | Integration | Local ESB software Installation | 9 | 2026-07-12 | 2026-07-21 | 2026-07-12 | 2026-07-21 | 2026-07-12 | 2026-07-18 | 100% | Completed | [8 empty] | SOFTWARE INSTALLATION
|  | Integration | DC-DR SYNC | 37 | 2026-10-15 | 2026-11-26 | 2026-10-15 | 2026-11-26 |  |  |  | Not Started | [8 empty] | Depend on availibility of LAN/WAN, to be10 - 12 weeks from design approval * TEMPRORY CONNECTION BETWEEN OT FW. TO MPLS CAN BE DONE TO ACHIVE THE SYCRONIZATION BETWEEN DC & DR
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26

## MADINAH Migration Plan-
| Workstream | Activity | Working Days | Planned Start | Planned Finish | Expected Start | Expected Finish | Actual Start / Expected Start | Actual Finish / Expected Finish | % Progress | Status | Root Cuase of Delay | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Remark | Planned Manpower | Actual Manpower | Resource Type | RESOURCE ALLOCATION | PRODUCTIVITY MATRIX |  | 7 Days Claendar
|  | Downstream Database Migration (1st Round) |  |  | Completed |  | Completed |  |  | 100% | Completed | [15 empty] | 6 Days Calendar
1st Batch (6 SS) | Upstream | SLD and DB Submission - Upstream | 1 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 100% | Completed | [15 empty] | 5 Days Calendar | SLD Submission | Batch 01 | 46166
| Upstream | Validation by SE - Upstream | 37 | 2026-05-12 | 2026-06-29 | 2026-05-12 | 2026-06-29 | 2026-05-12 | 2026-06-29 | 100% | Completed | [16 empty] | SLD Validation | Batch 01 | 46167
| Upstream | Telecom Rediness - Upstream |  | 2026-04-12 | 2026-07-26 | 2026-04-12 | 2026-07-28 |  | 2026-08-02 | 80% | In Progress | delayed due to "Madina LDC pretest" not started & New MPLS still not integrated with NOC, SAT with TNTD not started* | [7 empty] | *(DVM-E1-TSR ) should be received no later than 16-Jul-26 | [9 empty] | 46168
| Upstream | E2E - Upstream | 2 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-08-02 |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 1 |  |  | Leader - 1 (Wu Yang) | 3SS/DAY |  |  | E2E for Grid SS | Batch 01 | 46169
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-07-29 | 2026-07-30 | 2026-08-02 | 2026-08-03 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [6 empty] | E2E Rectification | Batch 01 | 46170
46288
2nd Batch (9 SS) | Upstream | SLD and DB Submission - Upstream | 1 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 100% | Completed | [16 empty] | SLD Submission | Batch 02 | 46288
| Upstream | Validation by SE - Upstream | 18 | 2026-06-11 | 2026-07-01 | 2026-06-11 | 2026-07-01 | 2026-06-11 | 2026-07-01 | 100% | Completed | [16 empty] | SLD Validation | Batch 02
| Upstream | E2E - Upstream | 3 | 2026-07-29 | 2026-08-02 | 2026-08-02 | 2026-08-04 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 1 |  |  | Leader - 1 (Wu Yang) | 3SS/DAY |  |  | E2E for Grid SS | Batch 02
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [6 empty] | E2E Rectification | Batch 02
3rd Batch (10 SS) | Upstream | SLD and DB Submission - Upstream | 7 | 2026-07-02 | 2026-07-09 | 2026-07-02 | 2026-07-09 | 2026-07-02 | 2026-07-09 | 100% | Completed | [16 empty] | SLD Submission | Batch 03
| Upstream | Validation by SE - Upstream | 2 | 2026-07-11 | 2026-07-12 | 2026-07-11 | 2026-07-12 | 2026-07-11 | 2026-07-11 | 100% | Completed | [16 empty] | SLD Validation | Batch 03
| Upstream | E2E - Upstream | 4 | 2026-08-03 | 2026-08-06 | 2026-08-05 | 2026-08-10 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 1 |  |  | Leader - 1 (Wu Yang) | 3SS/DAY |  |  | E2E for Grid SS | Batch 03
| Upstream | E2E Comments Rectification - Upstream | 4 | 2026-08-09 | 2026-08-12 | 2026-08-11 | 2026-08-16 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [6 empty] | E2E Rectification | Batch 03
4th Batch (11 SS) | Upstream | SLD and DB Submission - Upstream | 5 | 2026-07-13 | 2026-07-18 | 2026-07-13 | 2026-07-18 | 2026-07-12 | 2026-07-12 | 100% | Completed | [12 empty] | Total Expereienced Draftsmans - 1 (Li chengzhen) TOTAL SUPPORT DRAFTMAN -2 (Suilman, Mohamed Gamal) | 2/DAY APPROX |  |  | SLD Submission | Batch 04
| Upstream | Validation by SE - Upstream | 2 | 2026-07-19 | 2026-07-20 | 2026-07-19 | 2026-07-20 | 2026-07-13 | 2026-07-14 | 100% | Completed | [16 empty] | SLD Validation | Batch 04
| Upstream | E2E - Upstream | 4 | 2026-08-08 | 2026-08-12 | 2026-08-11 | 2026-08-17 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 2 |  |  | Leader - 1 (Wu Yang) Support - 1 | 3SS/DAY |  |  | E2E for Grid SS | Batch 04
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-13 | 2026-08-16 | 2026-08-18 | 2026-08-19 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [6 empty] | E2E Rectification | Batch 04
5th Batch (10 SS) | Upstream | SLD and DB Submission - Upstream | 5 | 2026-07-21 | 2026-07-26 | 2026-07-21 | 2026-07-26 | 2026-07-14 | 2026-07-14 | 100% | Completed | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 1 (Li chengzhen) TOTAL SUPPORT DRAFTMAN -2 (Suilman, Mohamed Gamal) | 2/DAY(SS) |  |  | SLD Submission | Batch 05
| Upstream | Validation by SE - Upstream | 2 | 2026-07-27 | 2026-07-28 | 2026-07-27 | 2026-07-28 | 2026-07-15 | 2026-07-16 | 100% | Completed | [8 empty] | 3 tabuk substation need a recheck | 1 | [6 empty] | SLD Validation | Batch 05
| Upstream | E2E - Upstream | 4 | 2026-08-13 | 2026-08-18 | 2026-08-18 | 2026-08-23 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 2 |  |  | Leader - 1 (Wu Yang) Support - 1 | 3SS/DAY |  |  | E2E for Grid SS | Batch 05
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-19 | 2026-08-20 | 2026-08-24 | 2026-08-25 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [6 empty] | E2E Rectification | Batch 05
6th Batch (10 SS) | Upstream | SLD and DB Submission - Upstream | 5 | 2026-07-29 | 2026-08-03 | 2026-07-29 | 2026-08-03 | 2026-07-16 | 2026-07-18 | 100% | Completed | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 1 (Li chengzhen) TOTAL SUPPORT DRAFTMAN -2 (Suilman, Mohamed Gamal) | 2/DAY(SS) |  |  | SLD Submission | Batch 06
| Upstream | Validation by SE - Upstream | 2 | 2026-08-04 | 2026-08-05 | 2026-08-04 | 2026-08-05 | 2026-07-19 | 2026-07-23 | 100% | Completed | [9 empty] | 1 | [6 empty] | SLD Validation | Batch 06
| Upstream | E2E - Upstream | 4 | 2026-08-19 | 2026-08-24 | 2026-08-24 | 2026-08-27 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 2 |  |  | Leader - 1 (Wu Yang) Support - 1 | 3SS/DAY |  |  | E2E for Grid SS | Batch 06
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-25 | 2026-08-26 | 2026-08-30 | 2026-08-31 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [6 empty] | E2E Rectification | Batch 06
7th Batch (10 SS) | Upstream | SLD and DB Submission - Upstream | 5 | 2026-08-06 | 2026-08-11 | 2026-08-06 | 2026-08-11 | 2026-07-19 | 2026-07-23 | 100% | Completed | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 1 (Li chengzhen) TOTAL SUPPORT DRAFTMAN -2 (Suilman, Mohamed Gamal) | 2/DAY(SS) |  |  | SLD Submission | Batch 07
| Upstream | Validation by SE - Upstream | 2 | 2026-08-12 | 2026-08-13 | 2026-08-12 | 2026-08-13 | 2026-07-23 |  | 30% | In Progress | [9 empty] | 1 | [6 empty] | SLD Validation | Batch 07
| Upstream | E2E - Upstream | 4 | 2026-08-25 | 2026-08-30 | 2026-08-29 | 2026-09-01 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 2 |  |  | Leader - 1 (Wu Yang) Support - 1 | 3SS/DAY |  |  | E2E for Grid SS | Batch 07
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [6 empty] | E2E Rectification | Batch 07
8th Batch (10 SS) | Upstream | SLD and DB Submission - Upstream | 4 | 2026-08-15 | 2026-08-18 | 2026-08-15 | 2026-08-18 | 2026-07-21 |  | 70% | In Progress | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 1 (Li chengzhen) TOTAL SUPPORT DRAFTMAN -2 (Suilman, Mohamed Gamal) | 3/DAY(SS) |  |  | SLD Submission | Batch 08
| Upstream | Validation by SE - Upstream | 2 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 |  |  |  | Not Started | [9 empty] | 1 | [6 empty] | SLD Validation | Batch 08
| Upstream | E2E - Upstream | 4 | 2026-08-31 | 2026-09-03 | 2026-09-02 | 2026-09-07 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 2 |  |  | Leader - 1 (Wu Yang) Support - 1 | 3SS/DAY |  |  | E2E for Grid SS | Batch 08
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [6 empty] | E2E Rectification | Batch 08
9th Batch (11 SS) | Upstream | SLD and DB Submission - Upstream | 3 | 2026-08-22 | 2026-08-24 | 2026-08-22 | 2026-08-24 | 2026-07-21 |  | 40% | In Progress | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 1 (Li chengzhen) TOTAL SUPPORT DRAFTMAN -2 (Suilman, Mohamed Gamal) | 4/DAY(SS) |  |  | SLD Submission | Batch 09
| Upstream | Validation by SE - Upstream | 2 | 2026-08-25 | 2026-08-26 | 2026-08-25 | 2026-08-26 |  |  |  | Not Started | [9 empty] | 1 | [6 empty] | SLD Validation | Batch 09
| Upstream | E2E - Upstream | 3 | 2026-09-05 | 2026-09-08 | 2026-09-08 | 2026-09-13 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 2 |  |  | Leader - 1 (Wu Yang) Support - 1 | 4SS/DAY |  |  | E2E for Grid SS | Batch 09
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-09 | 2026-09-10 | 2026-09-14 | 2026-09-15 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [6 empty] | E2E Rectification | Batch 09
10th Batch (11 SS) | Upstream | SLD and DB Submission - Upstream | 3 | 2026-08-27 | 2026-08-30 | 2026-08-27 | 2026-08-30 | 2026-07-21 |  | 55% | In Progress | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 1 (Li chengzhen) TOTAL SUPPORT DRAFTMAN -2 (Suilman, Mohamed Gamal) | 4/DAY(SS) |  |  | SLD Submission | Batch 10
| Upstream | Validation by SE - Upstream | 2 | 2026-08-31 | 2026-09-01 | 2026-08-31 | 2026-09-01 |  |  |  | Not Started | [8 empty] | Meet all prerequisites for STA and cutover activities. | 1 | [6 empty] | SLD Validation | Batch 10
| Upstream | E2E - Upstream | 4 | 2026-09-09 | 2026-09-14 | 2026-09-14 | 2026-09-17 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness | 2 |  |  | Leader - 1 (Wu Yang) Support - 1 | 3SS/DAY |  |  | E2E for Grid SS | Batch 10
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-15 | 2026-09-16 | 2026-09-20 | 2026-09-21 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [6 empty] | E2E Rectification | Batch 10
Migration | Migration | Alarm & Reporting Migration | 19 | 2026-08-03 | 2026-08-24 | 2026-08-03 | 2026-08-24 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration | 1 |  |  | Leader - 1(Yang tao)
| Migration | UI & Display Configuration | 19 | 2026-08-13 | 2026-09-03 | 2026-08-13 | 2026-09-03 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration | 1 |  |  | Leader - 1(Yang tao)
| Migration | Historian Migration | 60 | 2026-08-13 | 2026-10-22 | 2026-08-13 | 2026-10-22 |  |  |  | Not Started | [8 empty] | Depend on : *Data Structure & Analysis from SE Not Critical Path which will be completed during PAC | 1 |  |  | Leader - 1(Yang tao)
Cut Over - Upstream (Live-On) | Live On - Upstream | Cut Over（Batch 1:10） | 3 | 2026-09-28 | 2026-09-30 | 2026-09-30 | 2026-10-04 |  |  |  | Not Started | [8 empty] | *Completed SAT | 2 |  |  | Leader - 1 (Wu Yang) Support - 1
Noted: 1.If IT system integration is incomplete（IT System<-> Central ESB <-> Local ESB）will affect certain functionalities that require external data support. 2.We will provide an impact analysis of specific functional effects based on the data integration status before test.
5 Days Calendar
Training | Training | Training inside KSA | 30 | 2026-08-15 | 2026-09-27 | 2026-08-15 | 2026-09-27 |  |  |  | Not Started | [9 empty] | 1 |  |  | Leader - 1(Yang tao)
| Training | Training in Factory | 30 | 2026-11-01 | 2026-12-10 | 2026-11-05 | 2026-12-16 |  |  |  | Not Started | [8 empty] | After the cutover of all five-sites | 1
DERMS | DERMS | DERMS Software Installation | 30 | 2026-07-29 | 2026-09-01 | 2026-07-29 | 2026-09-01 |  |  |  | Not Started | [8 empty] | Firewall Configuration and required access rules shall be fully implemented and Verified. Network Access between relevant systems and sites shall be available and confirmed. Connection between DC & DR shall be completed to support DC/DR communication and failover test. All required ports, routing rules and security policies shall be provided before testing. Server Certificates shall be issued by SE.
| DERMS | DERMS SAT | 16 | 2026-09-02 | 2026-09-24 | 2026-09-02 | 2026-09-24 |  |  |  | Not Started | [8 empty] | Finalization of Interfaces with SE IT/OT Systems. Availability of DER Data.
DS(Batch 1) 6-GSS | Downstream | SLD and DB Validation Demo | 1 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 2026-07-12 |  |  | 100% | Completed | [9 empty] | 1
| Downstream | SLD and DB(Feeders of GSS Batch1) Feeders 120 (Graphic,Database,Link) | 6 | 2026-07-21 | 2026-07-27 | 2026-07-21 | 2026-07-27 | 2026-07-21 |  | 60% | In Progress | 150/170 | [7 empty] | Draft Man will mobilize on 7-Jul-26 | 1 |  |  | Total Expereienced Draftsmans - 1(Hu Yushuo) TOTAL SUPPORT DRAFTMAN -0 | 20/DAY
| Downstream | SLD and DB Validation | 5 | 2026-07-28 | 2026-08-02 | 2026-07-28 | 2026-08-02 |  |  |  | Not Started | [9 empty] | 1
1
DS(Batch 2) 9-GSS | Downstream | SLD and DB(Feeders of GSS Batch2) Feeders 210 (Graphic,Database,Link) | 5 | 2026-07-28 | 2026-08-02 | 2026-07-28 | 2026-08-02 |  |  |  | Not Started | [8 empty] | Draft Man will mobilize on 7-Jul-26 | 2 |  |  | Total Expereienced Draftsmans - 1(Hu Yushuo) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 42/DAY
| Downstream | SLD and DB Validation | 5 | 2026-08-03 | 2026-08-08 | 2026-08-03 | 2026-08-08 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 3) 10-GSS | Downstream | SLD and DB(Feeders of GSS Batch3) Feeders 220 (Graphic,Database,Link) | 5 | 2026-08-03 | 2026-08-08 | 2026-08-03 | 2026-08-08 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1(Hu Yushuo) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 44/DAY
| Downstream | SLD and DB Validation | 3 | 2026-08-09 | 2026-08-11 | 2026-08-09 | 2026-08-11 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 4) 11-GSS | Downstream | SLD and DB(Feeders of GSS Batch4) Feeders 220 (Graphic,Database,Link) | 3 | 2026-08-09 | 2026-08-11 | 2026-08-09 | 2026-08-11 |  |  |  | Not Started | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2(Hu Yushuo, Ye Wenhao) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 74/DAY
| Downstream | SLD and DB Validation | 3 | 2026-08-12 | 2026-08-15 | 2026-08-12 | 2026-08-15 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 5) 10-GSS | Downstream | SLD and DB(Feeders of GSS Batch5) Feeders 210 (Graphic,Database,Link) | 3 | 2026-08-12 | 2026-08-15 | 2026-08-12 | 2026-08-15 |  |  |  | Not Started | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2(Hu Yushuo, Ye Wenhao) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 70/day
| Downstream | SLD and DB Validation | 3 | 2026-08-16 | 2026-08-18 | 2026-08-16 | 2026-08-18 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 6) 10-GSS | Downstream | SLD and DB(Feeders of GSS Batch6) Feeders 210 (Graphic,Database,Link) | 3 | 2026-08-16 | 2026-08-18 | 2026-08-16 | 2026-08-18 |  |  |  | Not Started | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2(Hu Yushuo, Ye Wenhao) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 70/day
| Downstream | SLD and DB Validation | 3 | 2026-08-19 | 2026-08-22 | 2026-08-19 | 2026-08-22 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 7) 10-GSS | Downstream | SLD and DB(Feeders of GSS Batch7) Feeders 220 (Graphic,Database,Link) | 3 | 2026-08-19 | 2026-08-22 | 2026-08-19 | 2026-08-22 |  |  |  | Not Started | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2(Hu Yushuo, Ye Wenhao) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 74/day
| Downstream | SLD and DB Validation | 3 | 2026-08-23 | 2026-08-25 | 2026-08-23 | 2026-08-25 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 8) 10-GSS | Downstream | SLD and DB(Feeders of GSS Batch8) Feeders 200 (Graphic,Database,Link) | 3 | 2026-08-23 | 2026-08-25 | 2026-08-23 | 2026-08-25 |  |  |  | Not Started | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2(Hu Yushuo, Ye Wenhao) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 67/day
| Downstream | SLD and DB Validation | 3 | 2026-08-26 | 2026-08-29 | 2026-08-26 | 2026-08-29 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 9) 11-GSS | Downstream | SLD and DB(Feeders of GSS Batch9) Feeders 210 (Graphic,Database,Link) | 3 | 2026-08-26 | 2026-08-29 | 2026-08-26 | 2026-08-29 |  |  |  | Not Started | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2(Hu Yushuo, Ye Wenhao) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 70/day
| Downstream | SLD and DB Validation | 3 | 2026-08-30 | 2026-09-01 | 2026-08-30 | 2026-09-01 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 10) 11-GSS | Downstream | SLD and DB(Feeders of GSS Batch10) Feeders 200 (Graphic,Database,Link) | 3 | 2026-08-30 | 2026-09-01 | 2026-08-30 | 2026-09-01 |  |  |  | Not Started | [9 empty] | 3 |  |  | Total Expereienced Draftsmans - 2(Hu Yushuo, Ye Wenhao) TOTAL SUPPORT DRAFTMAN -1(ALOGAIMI) | 67/day
| Downstream | SLD and DB Validation | 3 | 2026-09-02 | 2026-09-05 | 2026-09-02 | 2026-09-05 |  |  |  | Not Started | [9 empty] | 1
DS(E2E) | Downstream | E2E for SFD (Total 9730 8% For Testing 780) | 31 | 2026-08-03 | 2026-09-14 | 2026-08-03 | 2026-09-14 |  |  |  | Not Started | [8 empty] | Depend on STC TELECOME CIRCUITS READINESS(INSTALLATION, HARDWARE, SOFTWARE, CONFIGURATION, TRAFFIC, REROUTING,....ETC) Depend on Availability of SE Field Engineer Start the E2E test after the approval for the first downstream batch E2E RMU Rate = 25 / Day | 2 |  |  | Leader - 1 (Bai liang) Support - 1 (Ali) | 25/day approx
CUTOVER | Live On - Downstream | Cuttover | 2 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-04 |  |  |  | Not Started | [8 empty] | After STC Success E2E | 2 |  |  | Leader - 1 (Bai liang) Support - 1 (Ali)
ADMS SAT | ADMS SAT | Hardware cybersecurity test | 2 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-13 |  |  |  | Not Started | [9 empty] | 3 |  |  | Team - 3 (Li chengzhen, Hu Yushuo, Ye Wenhao) Support -2 (Suilman, Gamal)
| ADMS SAT | Functional test - ADMS | 5 | 2026-09-10 | 2026-09-16 | 2026-09-14 | 2026-09-20 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Integration test | 5 | 2026-09-10 | 2026-09-16 | 2026-09-14 | 2026-09-20 |  |  |  | Not Started | [8 empty] | ADMS Integration Testing is dependent on the successful completion of all Phase 1 interface tests for the Centralized ESB. In accordance with the Local ESB schedule, the related integration preparation and coordination activities shall commence at least 45 days in advance. | 3
| ADMS SAT | Redundancy test | 2 | 2026-09-17 | 2026-09-20 | 2026-09-21 | 2026-09-22 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Stability | 3 | 2026-09-21 | 2026-09-24 | 2026-09-24 | 2026-09-28 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Regression test &unstructure test | 1 | 2026-09-27 | 2026-09-27 | 2026-09-29 | 2026-09-29 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Performance test | 1 | 2026-09-28 | 2026-09-28 | 2026-09-30 | 2026-09-30 |  |  |  | Not Started | [9 empty] | 3
Cyber Audit | Cyber Audit | Cyber Audit Phase1 | 16 | 2026-08-17 | 2026-09-07 | 2026-08-19 | 2026-09-09 |  |  |  | Not Started | [8 empty] | Cutover 1.Depend on the Approval for DTS-628 2.Depend on the telecom readiness
| Cyber Audit | Cyber Audit Phase2 | 20 | 2026-12-10 | 2027-01-06 | 2026-12-10 | 2027-01-06 |  |  |  | Not Started | [8 empty] | 1.Centralized Cybersecurity Audit 2.Depend on the SDCCs telecom readiness
Integration | Integration | DNMC Integration | 21 | 2026-09-07 | 2026-09-30 | 2026-09-09 | 2026-10-04 |  |  |  | Not Started | [8 empty] | 1.Depend on DNMC System Completed before 10 Aug, 2026 2.DNMC datapoint Scope to be confirmed by max 10, Aug 2026 3.DNMC <-----> DCC telecom completed by max 31 Aug, 2026 4.ICCP Configuration finished by 10 Aug, 2026 5.Testing（SDCC & DNMC ICCP Channel Testing,）finished by 20 Aug, 2026
| Integration | Local ESB software Installation | 9 | 2026-07-12 | 2026-07-21 | 2026-07-12 | 2026-07-21 | 2026-07-12 | 2026-07-21 | 100% | Completed | [8 empty] | SOFTWARE INSTALLATION
| Integration | DC-DR SYNC | 37 | 2026-10-15 | 2026-11-26 | 2026-10-15 | 2026-11-26 |  |  |  | Not Started | [8 empty] | Depend on availibility of LAN/WAN, to be10 - 12 weeks from design approval * TEMPRORY CONNECTION BETWEEN OT FW. TO MPLS CAN BE DONE TO ACHIVE THE SYCRONIZATION BETWEEN DC & DR
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26

## Jeddah Migration Plan
| Workstream | Activity | Working Days | Planned Start | Planned Finish | Expected Start | Expected Finish | Actual Start / Expected Start | Actual Finish / Expected Finish | % Progress | Status | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Root Cuase of Delay | Remark | Planned Manpower | Actual Manpower | Resource Type | RESOURCE ALLOCATION | PRODUCTIVITY MATRIX | 7 Days Claendar
|  | Database Migration for Upstream (1st Round) |  | 2026-05-18 | 2026-05-30 | 2026-05-18 | 2026-05-30 |  |  | 100% | Completed | [8 empty] | Makkah Database Migration (1st Round) in progress | [5 empty] | 6 Days Calendar
1st Batch (7 SS) | Upstream | SLD and DB - Upstream | 8 | 2026-06-27 | 2026-07-05 | 2026-06-27 | 2026-07-05 | 2026-06-27 | 2026-07-05 | 100% | Completed | [14 empty] | 5 Days Calendar | SLD Submission | Batch 01 | 2026-05-24
| Upstream | Software Installation | 12 | 2026-06-16 | 2026-06-29 | 2026-06-16 | 2026-06-29 | 2026-06-16 | 2026-07-29 | 100% | Completed | [17 empty] | 2026-05-25
| Upstream | Configuration of Network & Cyber Security | 11 | 2026-07-05 | 2026-07-16 | 2026-07-05 | 2026-07-23 |  | 2026-07-23 | 100% | Completed
| Upstream | Validation by SE - Upstream | 9 | 2026-07-06 | 2026-07-15 | 2026-07-06 | 2026-07-15 | 2026-07-06 | 2026-07-16 | 100% | Completed | [8 empty] | waiting for signs | [6 empty] | SLD Validation | Batch 01 | 2026-05-26
| Upstream | Telecom Rediness - Upstream |  | Started | 2026-07-26 | Started | 2026-07-26 |  |  | 94% | In Progress | [8 empty] | *Jeddah DR readiness *Depends on madinah SDCC TELEOM REDINESS 26-July considering all the prerequisite of achieving this date | [8 empty] | 2026-05-27
| Upstream | E2E - Upstream | 3 | 2026-07-27 | 2026-07-29 | 2026-07-27 | 2026-07-29 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Liu tianwen) | 3SS/DAY |  | E2E for Grid SS | Batch 01 | 2026-05-28
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-07-30 | 2026-08-02 | 2026-07-30 | 2026-08-02 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 01 | 2026-05-29
[28 empty] | Batch 02 | 2026-09-23
2nd Batch (15 SS) | Upstream | SLD and DB - Upstream | 3 | 2026-07-16 | 2026-07-19 | 2026-07-16 | 2026-07-19 | 2026-07-18 | 2026-07-21 | 100% | Completed | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Cheng yuheng) TOTAL SUPPORT DRAFTMAN -1 (Abdulrahman Gaees) | 5SS/DAY |  | SLD Submission | Batch 02
| Upstream | Validation by SE - Upstream | 3 | 2026-07-20 | 2026-07-22 | 2026-07-22 | 2026-07-28 | 2026-07-22 |  | 90% | Delayed | [7 empty] | delay caused by submission & validation(Batch 1) |  | 1 | [5 empty] | SLD Validation | Batch 02
| Upstream | E2E - Upstream | 5 | 2026-07-30 | 2026-08-05 | 2026-07-30 | 2026-08-05 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Liu tianwen) | 3SS/DAY |  | E2E for Grid SS | Batch 02
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-06 | 2026-08-09 | 2026-08-06 | 2026-08-09 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 02
Batch 03
3rd Batch (19 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-07-23 | 2026-07-28 | 2026-07-29 | 2026-08-03 | 2026-07-22 |  | 60% | In Progress | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 1 (Cheng yuheng) TOTAL SUPPORT DRAFTMAN -3(Kamran,Hamza Amjad, Azizuddin) | 4SS/DAY |  | SLD Submission | Batch 03
| Upstream | Validation by SE - Upstream | 3 | 2026-07-29 | 2026-08-01 | 2026-08-04 | 2026-08-06 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 03
| Upstream | E2E - Upstream | 7 | 2026-08-06 | 2026-08-16 | 2026-08-08 | 2026-08-16 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Liu tianwen) | 3SS/DAY |  | E2E for Grid SS | Batch 03
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-17 | 2026-08-18 | 2026-08-17 | 2026-08-18 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 03
Batch 04
4th Batch (20 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-08-02 | 2026-08-06 | 2026-08-08 | 2026-08-12 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 1 (Cheng yuheng) TOTAL SUPPORT DRAFTMAN -3(Kamran,Hamza Amjad, Azizuddin) | 4SS/DAY |  | SLD Submission | Batch 04
| Upstream | Validation by SE - Upstream | 3 | 2026-08-08 | 2026-08-10 | 2026-08-13 | 2026-08-16 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 04
| Upstream | E2E - Upstream | 7 | 2026-08-17 | 2026-08-25 | 2026-08-17 | 2026-08-25 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Liu tianwen) | 3SS/DAY |  | E2E for Grid SS | Batch 04
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-26 | 2026-08-27 | 2026-08-26 | 2026-08-27 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 04
Batch 05
5th Batch (19 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-08-11 | 2026-08-16 | 2026-08-17 | 2026-08-22 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 1 (Cheng yuheng) TOTAL SUPPORT DRAFTMAN -3(Kamran,Hamza Amjad, Azizuddin) | 4SS/DAY |  | SLD Submission | Batch 05
| Upstream | Validation by SE - Upstream | 3 | 2026-08-17 | 2026-08-19 | 2026-08-23 | 2026-08-25 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 05
| Upstream | E2E - Upstream | 7 | 2026-08-26 | 2026-09-03 | 2026-08-26 | 2026-09-03 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Liu tianwen) | 3/DAY(SS) |  | E2E for Grid SS | Batch 05
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-06 | 2026-09-07 | 2026-09-06 | 2026-09-07 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 05
Batch 06
6th Batch (22 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-08-20 | 2026-08-25 | 2026-08-26 | 2026-08-31 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 1 (Cheng yuheng) TOTAL SUPPORT DRAFTMAN -3(Kamran,Hamza Amjad, Azizuddin) | 5SS/DAY |  | SLD Submission | Batch 06
| Upstream | Validation by SE - Upstream | 3 | 2026-08-26 | 2026-08-29 | 2026-09-01 | 2026-09-03 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 06
| Upstream | E2E - Upstream | 7 | 2026-09-05 | 2026-09-14 | 2026-09-05 | 2026-09-14 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Liu tianwen) | 3/DAY(SS) APPROX |  | E2E for Grid SS | Batch 06
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-15 | 2026-09-16 | 2026-09-15 | 2026-09-16 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 06
Batch 07
7th Batch (17 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-08-30 | 2026-09-03 | 2026-09-05 | 2026-09-09 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 1 (Cheng yuheng) TOTAL SUPPORT DRAFTMAN -3(Kamran,Hamza Amjad, Azizuddin) | 4SS/DAY APPROX |  | SLD Submission | Batch 07
| Upstream | Validation by SE - Upstream | 3 | 2026-09-05 | 2026-09-07 | 2026-09-10 | 2026-09-13 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 07
| Upstream | E2E - Upstream | 6 | 2026-09-15 | 2026-09-22 | 2026-09-15 | 2026-09-22 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Liu tianwen) | 3/DAY(SS) |  | E2E for Grid SS | Batch 07
| Upstream | E2E Comments Rectification - Upstream | 1 | 2026-09-23 | 2026-09-24 | 2026-09-23 | 2026-09-24 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 07
Batch 08
8th Batch (20 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-09-08 | 2026-09-13 | 2026-09-14 | 2026-09-19 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 1 (Cheng yuheng) TOTAL SUPPORT DRAFTMAN -3(Kamran,Hamza Amjad, Azizuddin) | 4SS/DAY APPROX |  | SLD Submission | Batch 08
| Upstream | Validation by SE - Upstream | 3 | 2026-09-14 | 2026-09-16 | 2026-09-20 | 2026-09-22 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 08
| Upstream | E2E - Upstream | 6 | 2026-09-23 | 2026-10-01 | 2026-09-23 | 2026-10-01 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Liu tianwen) | 3SS/DAY |  | E2E for Grid SS | Batch 08
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-10-04 | 2026-10-05 | 2026-10-04 | 2026-10-05 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 08
Batch 09
9th Batch (19 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-09-17 | 2026-09-22 | 2026-09-23 | 2026-09-28 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 1 (Cheng yuheng) TOTAL SUPPORT DRAFTMAN -3(Kamran,Hamza Amjad, Azizuddin) | 4SS/DAY |  | SLD Submission | Batch 09
| Upstream | Validation by SE - Upstream | 2 | 2026-09-23 | 2026-09-26 | 2026-09-29 | 2026-10-01 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 09
| Upstream | E2E - Upstream | 6 | 2026-10-03 | 2026-10-11 | 2026-10-03 | 2026-10-11 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Liu tianwen) | 3/DAY(SS) APPROX |  | E2E for Grid SS | Batch 09
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-10-12 | 2026-10-13 | 2026-10-12 | 2026-10-13 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 09
|  | - Upstream | [25 empty] | Batch 10
10th Batch (22 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-09-27 | 2026-10-01 | 2026-10-03 | 2026-10-07 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 1 (Cheng yuheng) TOTAL SUPPORT DRAFTMAN -3(Kamran,Hamza Amjad, Azizuddin) | 5SS/DAY |  | SLD Submission | Batch 10
| Upstream | Validation by SE - Upstream | 3 | 2026-10-03 | 2026-10-05 | 2026-10-08 | 2026-10-11 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 10
| Upstream | E2E - Upstream | 8 | 2026-10-12 | 2026-10-21 | 2026-10-12 | 2026-10-21 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Liu tianwen) | 33SS/DAY |  | E2E for Grid SS | Batch 10
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-10-22 | 2026-10-25 | 2026-10-22 | 2026-10-25 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 10
Migration | Migration | Alarm & Reporting Migration | 19 | 2026-10-08 | 2026-10-29 | 2026-10-08 | 2026-10-29 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration | 1 |  |  | Leader - 1(Luo geshibu) Support - 1(Jia wei)
| Migration | UI & Display Configuration | 19 | 2026-08-19 | 2026-09-09 | 2026-08-19 | 2026-09-09 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration | 1 |  |  | Leader - 1(Luo geshibu) Support - 1(Jia wei)
| Migration | Historian Migration | 66 | 2026-08-19 | 2026-11-03 | 2026-08-19 | 2026-11-03 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration *Data Structure & Analysis from SE | 1 |  |  | Leader - 1(Luo geshibu) Support - 1(Jia wei)
Cut Over - Upstream (Live-On) | Live On - Upstream | Cut Over（Batch1-10） | 3 | 2026-10-26 | 2026-10-28 | 2026-10-26 | 2026-10-28 |  |  |  | Not Started | [8 empty] | *Completed SAT | 1 |  |  | Leader - 1 (Liu tianwen)
Upstream SAT
Training | Training | Training inside KSA | 30 | 2026-08-15 | 2026-09-24 | 2026-08-15 | 2026-09-24 |  |  |  | Not Started | [9 empty] | 1 |  |  | Leader - 1(Luo geshibu) Support - 1(Jia wei)
| Training | Training in Factory | 30 | 2026-11-01 | 2026-12-10 | 2026-11-01 | 2026-12-10 |  |  |  | Not Started | [8 empty] | After the cutover of all five-sites | 1
DERMS | DERMS | DERMS Software Installation | 19 | 2026-08-12 | 2026-09-02 | 2026-08-12 | 2026-09-02 |  |  |  | Not Started | [8 empty] | Firewall Configuration and required access rules shall be fully implemented and Verified. Network Access between relevant systems and sites shall be available and confirmed. Connection between DC & DR shall be completed to support DC/DR communication and failover test. All required ports, routing rules and security policies shall be provided before testing. Server Certificates shall be issued by SE. | 1
| DERMS | DERMS SAT | 15 | 2026-09-23 | 2026-10-14 | 2026-09-23 | 2026-10-14 |  |  |  | Not Started | [8 empty] | Finalization of Interfaces with SE IT/OT Systems. Availability of DER Data. | 1
DS(Batch 1) 7-GSS | Downstream | SLD and DB Validation Demo | 1 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 100% | Completed
| Downstream | SLD and DB(Feeders of GSS Batch1) Feeders 150 (Graphic,Database,Link) | 10 | 2026-07-21 | 2026-08-01 | 2026-07-21 | 2026-08-01 | 2026-07-21 |  | 18% | In Progress | [8 empty] | Draft Man will mobilize on 7-Jul-26 | 3 |  |  | Total Expereienced Draftsmans - 1(Li xiangyun) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI, Abdulrahman Alamri) | 15/DAY
| Downstream | SLD and DB Validation | 4 | 2026-08-02 | 2026-08-05 | 2026-08-02 | 2026-08-05 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 2) 15 -GSS | Downstream | SLD and DB(Feeders of GSS Batch2) Feeders 300 (Graphic,Database,Link) | 7 | 2026-08-02 | 2026-08-09 | 2026-08-02 | 2026-08-09 |  |  |  | Not Started | [8 empty] | Draft Man will mobilize on 7-Jul-26 | 3 |  |  | Total Expereienced Draftsmans - 1(Li xiangyun) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI, Abdulrahman Alamri) | 43/DAY
| Downstream | SLD and DB Validation | 5 | 2026-08-10 | 2026-08-15 | 2026-08-10 | 2026-08-15 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 3) 19-GSS | Downstream | SLD and DB(Feeders of GSS Batch3) Feeders 380 (Graphic,Database,Link) | 5 | 2026-08-10 | 2026-08-15 | 2026-08-10 | 2026-08-15 |  |  |  | Not Started | [9 empty] | 5 |  |  | Total Expereienced Draftsmans - 2(Li xiangyun, Jia wei ) TOTAL SUPPORT DRAFTMAN -3(ALOGAIMI, Abdulrahman Alamri, Musa Jan) | 76/DAY
| Downstream | SLD and DB Validation | 5 | 2026-08-16 | 2026-08-20 | 2026-08-16 | 2026-08-20 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 4) 20-GSS | Downstream | SLD and DB(Feeders of GSS Batch4) Feeders 400 (Graphic,Database,Link) | 7 | 2026-08-16 | 2026-08-23 | 2026-08-16 | 2026-08-23 |  |  |  | Not Started | [9 empty] | 5 |  |  | Total Expereienced Draftsmans - 2(Li xiangyun, Jia wei ) TOTAL SUPPORT DRAFTMAN -3(ALOGAIMI, Abdulrahman Alamri, Musa Jan) | 58/day
| Downstream | SLD and DB Validation | 5 | 2026-08-24 | 2026-08-29 | 2026-08-24 | 2026-08-29 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 5) 19-GSS | Downstream | SLD and DB(Feeders of GSS Batch5) Feeders 380 (Graphic,Database,Link) | 5 | 2026-08-24 | 2026-08-29 | 2026-08-24 | 2026-08-29 |  |  |  | Not Started | [9 empty] | 5 |  |  | Total Expereienced Draftsmans - 2(Li xiangyun, Jia wei ) TOTAL SUPPORT DRAFTMAN -3(ALOGAIMI, Abdulrahman Alamri, Musa Jan) | 76/day
| Downstream | SLD and DB Validation | 5 | 2026-08-30 | 2026-09-03 | 2026-08-30 | 2026-09-03 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 6) 22-GSS | Downstream | SLD and DB(Feeders of GSS Batch6) Feeders 450 (Graphic,Database,Link) | 7 | 2026-08-30 | 2026-09-06 | 2026-08-30 | 2026-09-06 |  |  |  | Not Started | [9 empty] | 5 |  |  | Total Expereienced Draftsmans - 2(Li xiangyun, Jia wei ) TOTAL SUPPORT DRAFTMAN -3(ALOGAIMI, Abdulrahman Alamri, Musa Jan) | 64/day
| Downstream | SLD and DB Validation | 5 | 2026-09-07 | 2026-09-12 | 2026-09-07 | 2026-09-12 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 7) 17-GSS | Downstream | SLD and DB(Feeders of GSS Batch7) Feeders 350 (Graphic,Database,Link) | 5 | 2026-09-07 | 2026-09-12 | 2026-09-07 | 2026-09-12 |  |  |  | Not Started | [9 empty] | 5 |  |  | Total Expereienced Draftsmans - 2(Li xiangyun, Jia wei ) TOTAL SUPPORT DRAFTMAN -3(ALOGAIMI, Abdulrahman Alamri, Musa Jan) | 70/day
| Downstream | SLD and DB Validation | 5 | 2026-09-13 | 2026-09-17 | 2026-09-13 | 2026-09-17 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 8) 20-GSS | Downstream | SLD and DB(Feeders of GSS Batch8) Feeders 400 (Graphic,Database,Link) | 6 | 2026-09-13 | 2026-09-19 | 2026-09-13 | 2026-09-19 |  |  |  | Not Started | [9 empty] | 5 |  |  | Total Expereienced Draftsmans - 2(Li xiangyun, Jia wei ) TOTAL SUPPORT DRAFTMAN -3(ALOGAIMI, Abdulrahman Alamri, Musa Jan) | 67/day
| Downstream | SLD and DB Validation | 5 | 2026-09-20 | 2026-09-24 | 2026-09-20 | 2026-09-24 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 9) 19-GSS | Downstream | SLD and DB(Feeders of GSS Batch9) Feeders 380 (Graphic,Database,Link) | 5 | 2026-09-20 | 2026-09-24 | 2026-09-20 | 2026-09-24 |  |  |  | Not Started | [9 empty] | 5 |  |  | Total Expereienced Draftsmans - 2(Li xiangyun, Jia wei ) TOTAL SUPPORT DRAFTMAN -3(ALOGAIMI, Abdulrahman Alamri, Musa Jan) | 76/day
| Downstream | SLD and DB Validation | 5 | 2026-09-26 | 2026-09-30 | 2026-09-26 | 2026-09-30 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 10) 22-GSS | Downstream | SLD and DB(Feeders of GSS Batch10) Feeders 450 (Graphic,Database,Link) | 6 | 2026-09-26 | 2026-10-01 | 2026-09-26 | 2026-10-01 |  |  |  | Not Started | [9 empty] | 5 |  |  | Total Expereienced Draftsmans - 2(Li xiangyun, Jia wei ) TOTAL SUPPORT DRAFTMAN -3(ALOGAIMI, Abdulrahman Alamri, Musa Jan) | 75/day
| Downstream | SLD and DB Validation | 4 | 2026-10-03 | 2026-10-06 | 2026-10-03 | 2026-10-06 |  |  |  | Not Started | [9 empty] | 1
DS(E2E) | Downstream | E2E for SFD (Total 11985 8% For Testing 960) | 45 | 2026-08-06 | 2026-10-07 | 2026-08-06 | 2026-10-07 |  |  |  | Not Started | [8 empty] | Depend on STC TELECOME CIRCUITS READINESS(INSTALLATION, HARDWARE, SOFTWARE, CONFIGURATION, TRAFFIC, REROUTING,....ETC) Depend on Availability of SE Field Engineer Start the E2E test after the approval for the first downstream batch. E2E RMU Rate = 21 / Day | 2 |  |  | Leader - 1 (Qiao zhongjie) Support - 1 (Xiong donghai) | 21/DAY
CUTOVER | Live On - Downstream | Cuttover | 3 | 2026-10-27 | 2026-10-31 | 2026-11-03 | 2026-11-07 |  |  |  | Not Started | [8 empty] | After STC Success E2E | 2 |  |  | Leader - 1 (Qiao zhongjie) Support - 1 (Xiong donghai)
ADMS SAT | ADMS SAT | Hardware cybersecurity test | 2 | 2026-10-07 | 2026-10-08 | 2026-10-12 | 2026-10-13 |  |  |  | Not Started | [9 empty] | 3 |  |  | Team - 4 (Jia wei, Cheng yuheng, Li xiangyun, Lijia) Support -4 (Abdulrahman Alamri,Kamran,Hamza Amjad, Azizuddin)
| ADMS SAT | Functional test - ADMS | 5 | 2026-10-10 | 2026-10-15 | 2026-10-14 | 2026-10-21 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Integration test | 5 | 2026-10-10 | 2026-10-15 | 2026-10-14 | 2026-10-21 |  |  |  | Not Started | [8 empty] | ADMS Integration Testing is dependent on the successful completion of all Phase 1 interface tests for the Centralized ESB. In accordance with the Local ESB schedule, the related integration preparation and coordination activities shall commence at least 45 days in advance. | 3
| ADMS SAT | Redundancy test | 1 | 2026-10-17 | 2026-10-18 | 2026-10-22 | 2026-10-25 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Stability | 4 | 2026-10-19 | 2026-10-24 | 2026-10-26 | 2026-10-31 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Regression test &unstructure test | 1 | 2026-10-25 | 2026-10-25 | 2026-11-01 | 2026-11-01 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Performance test | 1 | 2026-10-26 | 2026-10-26 | 2026-11-02 | 2026-11-02 |  |  |  | Not Started | [9 empty] | 3
Cyber Audit | Cyber Audit | Cyber Audit Phase1 | 16 | 2026-09-15 | 2026-10-06 | 2026-09-20 | 2026-10-11 |  |  |  | Not Started | [8 empty] | Cutover 1.Depend on the Approval for DTS-628 2.Depend on the telecom readiness
| Cyber Audit | Cyber Audit Phase2 | 20 | 2026-12-10 | 2027-01-06 | 2026-12-10 | 2027-01-06 |  |  |  | Not Started | [8 empty] | 1.Centralized Cybersecurity Audit 2.Depend on the SDCCs telecom readiness
Integration | Integration | DNMC Integration | 21 | 2026-10-05 | 2026-10-28 | 2026-10-05 | 2026-10-28 |  |  |  | Not Started | [8 empty] | 1.Depend on DNMC System Completed before 10 Aug, 2026 2.DNMC datapoint Scope to be confirmed by max 10, Aug 2026 3.DNMC <-----> DCC telecom completed by max 31 Aug, 2026 4.ICCP Configuration finished by 10 Aug, 2026 5.Testing（SDCC & DNMC ICCP Channel Testing,）finished by 20 Aug, 2026
| Integration | Local ESB software Installation | 9 | 2026-07-12 | 2026-07-21 | 2026-07-12 | 2026-07-21 | 2026-07-12 | 2026-07-19 | 100% | Completed | [8 empty] | SOFTWARE INSTALLATION
| Integration | DC-DR SYNC | 37 | 2026-10-15 | 2026-11-26 | 2026-10-15 | 2026-11-26 |  |  |  | Not Started | [8 empty] | Depend on availibility of LAN/WAN, to be10 - 12 weeks from design approval * TEMPRORY CONNECTION BETWEEN OT FW. TO MPLS CAN BE DONE TO ACHIVE THE SYCRONIZATION BETWEEN DC & DR
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26

## AES Resource Plan (hidden)
City | Planned Start | Planned Finish | Duration (Days) | AES Engineers | Main / Primary Coverage | DR Coverage | Remote-Site Coverage | Notes | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26
JEDDAH | 2026-07-27 | 2026-10-25 | 91 | 2 | Main Control Center – Jeddah | Disaster Recovery – Madinah | — |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
MAKKAH | 2026-08-02 | 2026-10-13 | 73 | 2 | Main Control Center – Makkah | DR – Jeddah (Existing) | Taif |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
MADINAH | 2026-07-27 | 2026-09-27 | 63 | 2 | Main (Existing) – Madinah | DR (Existing) – Jeddah | Madinah LDC / Tabuk |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
ABHA | 2026-08-02 | 2026-09-27 | 57 | 4 | Main Control Center – Abha | Disaster Recovery – Jizan | Abha SRCC / Bisha |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
JIZAN | 2026-07-27 | 2026-09-15 | 51 | 2 | Main (Existing) – Jizan | DR (Existing) – Abha | Jizan LDC / Najran |  | 2026-07-27: 2; 2026-08-03: 2; 2026-08-10: 2; 2026-08-17: 2; 2026-08-24: 2; 2026-08-31: 2; 2026-09-07: 2; 2026-09-14: 2
[9 empty] | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26
[9 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 4 | 4 | 4 | 2 | 0

## Makkah Migration Plan
| Workstream | Activity | Working Days | Planned Start | Planned Finish | Expected Start | Expected Finish | Actual Start / Expected Start | Actual Finish / Expected Finish | % Progress | Status | Root Cuase of Delay | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Remark | Planned Manpower | Actual Manpower | Resource Type | RESOURCE ALLOCATION | PRODUCTIVITY MATRIX | 7 Days Claendar
|  | Database Migration (1st Round) |  | 2026-05-06 | 2026-05-21 | 2026-05-06 | 2026-05-21 |  |  | 100% | Completed | [8 empty] | Makkah Database Migration (1st Round) in progress | [5 empty] | 6 Days Calendar
1st Batch (6 SS) | Upstream | SLD and DB - Upstream | 17 | 2026-06-27 | 2026-07-15 | 2026-06-27 | 2026-07-16 |  | 2026-07-16 | 100% | Completed | [8 empty] | will be submitted by 15 july 2026 | 1 |  |  | Total Expereienced Draftsmans - 1 (Sun zhongjie) |  | 5 Days Calendar | SLD Submission | Batch 01 | 2026-05-24
| Upstream | Software Installation | 25 | 2026-06-17 | 2026-07-15 | 2026-06-17 | 2026-07-15 | 2026-06-17 | 2026-07-15 | 100% | Completed
| Upstream | Configuration of Network & Cyber Security | 14 | 2026-07-16 | 2026-08-01 | 2026-07-16 | 2026-08-01 | 2026-07-16 |  | 30% | In Progress | [8 empty] | *Extension of Working Hours to be extending till 9:00 PM on daily basis including weekend Friday and Saturday
| Upstream | Validation by SE - Upstream | 3 | 2026-07-16 | 2026-07-19 | 2026-07-18 | 2026-07-20 | 2026-07-18 | 2026-07-20 | 100% | Completed | [8 empty] | will be send for review by 15 july | [6 empty] | SLD Validation | Batch 01 | 2026-05-25
| Upstream | Telecom Rediness - Upstream |  | Started | 2026-07-29 | Started | 2026-07-29 |  |  | 96% | In Progress | delayed due to TSRs related to DVM IP addresses, along with the E1 TSRs still not recieved. | [7 empty] | *(DVM-E1-TSR ) should be received no later than 16-Jul-26 | [8 empty] | 2026-05-26
| Upstream | E2E - Upstream | 2 | 2026-08-02 | 2026-08-03 | 2026-08-02 | 2026-08-03 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Ma long) | 3SS/DAY |  | E2E for Grid SS | Batch 01 | 2026-05-27
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-04 | 2026-08-05 | 2026-08-04 | 2026-08-05 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 01 | 2026-05-28
|  | - Upstream | [25 empty] | Batch 02 | 2026-09-23
2nd Batch (9 SS) | Upstream | SLD and DB - Upstream | 7 | 2026-07-20 | 2026-07-27 | 2026-07-21 | 2026-07-27 | 2026-07-21 |  | 65% | In Progress | delayed in predecessor | [8 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Sun zhongjie) TOTAL SUPPORT DRAFTMAN -1 (Abdulrahman Gaees) |  |  | SLD Submission | Batch 02 | 46288
| Upstream | Validation by SE - Upstream | 3 | 2026-07-28 | 2026-07-30 | 2026-07-28 | 2026-07-30 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 02
| Upstream | E2E - Upstream | 3 | 2026-08-04 | 2026-08-06 | 2026-08-04 | 2026-08-06 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Ma long) | 3SS/DAY |  | E2E for Grid SS | Batch 02
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-09 | 2026-08-10 | 2026-08-09 | 2026-08-10 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 02
|  | - Upstream | [25 empty] | Batch 03
3rd Batch (15 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-08-01 | 2026-08-05 | 2026-08-01 | 2026-08-05 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Sun zhongjie) TOTAL SUPPORT DRAFTMAN -1 (Abdulrahman Gaees) | 3SS/DAY |  | SLD Submission | Batch 03
| Upstream | Validation by SE - Upstream | 2 | 2026-08-06 | 2026-08-08 | 2026-08-06 | 2026-08-08 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 03
| Upstream | E2E - Upstream | 5 | 2026-08-09 | 2026-08-13 | 2026-08-09 | 2026-08-13 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Ma long) | 3SS/DAY |  | E2E for Grid SS | Batch 03
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-16 | 2026-08-17 | 2026-08-16 | 2026-08-17 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 03
|  | - Upstream | [25 empty] | Batch 04
4th Batch (15 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-08-09 | 2026-08-13 | 2026-08-09 | 2026-08-13 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Sun zhongjie) TOTAL SUPPORT DRAFTMAN -1 (Abdulrahman Gaees) | 3SS/DAY |  | SLD Submission | Batch 04
| Upstream | Validation by SE - Upstream | 2 | 2026-08-15 | 2026-08-16 | 2026-08-15 | 2026-08-16 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 04
| Upstream | E2E - Upstream | 5 | 2026-08-17 | 2026-08-23 | 2026-08-17 | 2026-08-23 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Ma long) | 3SS/DAY |  | E2E for Grid SS | Batch 04
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 04
|  | - Upstream | [25 empty] | Batch 05
5th Batch (15 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-08-17 | 2026-08-22 | 2026-08-17 | 2026-08-22 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Sun zhongjie) TOTAL SUPPORT DRAFTMAN -1 (Abdulrahman Gaees) | 3SS/DAY |  | SLD Submission | Batch 05
| Upstream | Validation by SE - Upstream | 2 | 2026-08-23 | 2026-08-24 | 2026-08-23 | 2026-08-24 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 05
| Upstream | E2E - Upstream | 5 | 2026-08-25 | 2026-08-31 | 2026-08-25 | 2026-08-31 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Ma long) | 3SS/DAY |  | E2E for Grid SS | Batch 05
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-01 | 2026-09-02 | 2026-09-01 | 2026-09-02 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 05
|  | - Upstream | [25 empty] | Batch 06
6th Batch (15 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-08-25 | 2026-08-30 | 2026-08-25 | 2026-08-30 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Sun zhongjie) TOTAL SUPPORT DRAFTMAN -1 (Abdulrahman Gaees) | 3SS/DAY |  | SLD Submission | Batch 06
| Upstream | Validation by SE - Upstream | 2 | 2026-08-31 | 2026-09-01 | 2026-08-31 | 2026-09-01 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 06
| Upstream | E2E - Upstream | 5 | 2026-09-02 | 2026-09-08 | 2026-09-02 | 2026-09-08 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Ma long) | 3SS/DAY |  | E2E for Grid SS | Batch 06
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-09 | 2026-09-10 | 2026-09-09 | 2026-09-10 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 06
|  | - Upstream | [25 empty] | Batch 07
7th Batch (15 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-09-02 | 2026-09-07 | 2026-09-02 | 2026-09-07 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Sun zhongjie) TOTAL SUPPORT DRAFTMAN -1 (Abdulrahman Gaees) | 3SS/DAY |  | SLD Submission | Batch 07
| Upstream | Validation by SE - Upstream | 2 | 2026-09-08 | 2026-09-09 | 2026-09-08 | 2026-09-09 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 07
| Upstream | E2E - Upstream | 5 | 2026-09-10 | 2026-09-16 | 2026-09-10 | 2026-09-16 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Ma long) | 3SS/DAY |  | E2E for Grid SS | Batch 07
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-17 | 2026-09-20 | 2026-09-17 | 2026-09-20 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 07
|  | - Upstream | [25 empty] | Batch 08
8th Batch (15 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-09-10 | 2026-09-15 | 2026-09-10 | 2026-09-15 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Sun zhongjie) TOTAL SUPPORT DRAFTMAN -1 (Abdulrahman Gaees) | 3SS/DAY |  | SLD Submission | Batch 08
| Upstream | Validation by SE - Upstream | 2 | 2026-09-16 | 2026-09-17 | 2026-09-16 | 2026-09-17 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 08
| Upstream | E2E - Upstream | 3 | 2026-09-19 | 2026-09-23 | 2026-09-19 | 2026-09-23 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Ma long) | 3SS/DAY |  | E2E for Grid SS | Batch 08
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-09-24 | 2026-09-27 | 2026-09-24 | 2026-09-27 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 08
|  | - Upstream | [25 empty] | Batch 09
9th Batch (15 SS) | Upstream | SLD and DB - Upstream | 4 | 2026-09-19 | 2026-09-23 | 2026-09-19 | 2026-09-23 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Sun zhongjie) TOTAL SUPPORT DRAFTMAN -1 (Abdulrahman Gaees) | 4SS/DAY |  | SLD Submission | Batch 09
| Upstream | Validation by SE - Upstream | 2 | 2026-09-24 | 2026-09-26 | 2026-09-24 | 2026-09-26 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 09
| Upstream | E2E - Upstream | 5 | 2026-09-27 | 2026-10-01 | 2026-09-27 | 2026-10-01 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Ma long) | 3SS/DAY |  | E2E for Grid SS | Batch 09
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-10-04 | 2026-10-05 | 2026-10-04 | 2026-10-05 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 09
|  | - Upstream | [25 empty] | Batch 10
10th Batch (15 SS) | Upstream | SLD and DB - Upstream | 5 | 2026-09-27 | 2026-10-01 | 2026-09-27 | 2026-10-01 |  |  |  | Not Started | [9 empty] | 2 |  |  | Total Expereienced Draftsmans - 1 (Sun zhongjie) TOTAL SUPPORT DRAFTMAN -1 (Abdulrahman Gaees) | 3SS/DAY |  | SLD Submission | Batch 10
| Upstream | Validation by SE - Upstream | 2 | 2026-10-03 | 2026-10-04 | 2026-10-03 | 2026-10-04 |  |  |  | Not Started | [9 empty] | 1 | [5 empty] | SLD Validation | Batch 10
| Upstream | E2E - Upstream | 5 | 2026-10-05 | 2026-10-11 | 2026-10-05 | 2026-10-11 |  |  |  | Not Started | [8 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 1 |  |  | Leader - 1 (Ma long) | 3SS/DAY |  | E2E for Grid SS | Batch 10
| Upstream | E2E Comments Rectification - Upstream | 2 | 2026-10-12 | 2026-10-13 | 2026-10-12 | 2026-10-13 |  |  |  | Not Started | [8 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 1 | [5 empty] | E2E Rectification | Batch 10
Migration | Migration | Alarm & Reporting Migration | 19 | 2026-09-13 | 2026-10-04 | 2026-09-13 | 2026-10-04 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration | 1 |  |  | Leader - 1 (Wu xiaorui)
| Migration | UI & Display Configuration | 19 | 2026-08-22 | 2026-09-12 | 2026-08-22 | 2026-09-12 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration | 1 |  |  | Leader - 1 (Wu xiaorui)
| Migration | Historian Migration | 65 | 2026-08-22 | 2026-11-04 | 2026-08-22 | 2026-11-04 |  |  |  | Not Started | [8 empty] | Depend on : *1st Round of Database Migration *Data Structure & Analysis from SE | 1 |  |  | Leader - 1 (Wu xiaorui)
Cut Over - Upstream (Live-On) | Live On - Upstream | Cut Over（Batch1-10） | 3 | 2026-10-14 | 2026-10-18 | 2026-10-14 | 2026-10-18 |  |  |  | Not Started | [8 empty] | *Completed SAT | 1 |  |  | Leader - 1 (Ma long)
Training | Training | Training inside KSA | 30 | 2026-08-15 | 2026-09-24 | 2026-08-15 | 2026-09-24 |  |  |  | Not Started | [9 empty] | 1 |  |  | Leader - 1 (Wu xiaorui)
| Training | Training in Factory | 30 | 2026-10-25 | 2026-12-03 | 2026-10-25 | 2026-12-03 |  |  |  | Not Started | [8 empty] | After the cutover of all five-sites | 1
DERMS | DERMS | DERMS Software Installation | 19 | 2026-08-26 | 2026-09-16 | 2026-08-26 | 2026-09-16 |  |  |  | Not Started | [8 empty] | Firewall Configuration and required access rules shall be fully implemented and Verified. Network Access between relevant systems and sites shall be available and confirmed. Connection between DC & DR shall be completed to support DC/DR communication and failover test. All required ports, routing rules and security policies shall be provided before testing. Server Certificates shall be issued by SE.
| DERMS | DERMS SAT | 16 | 2026-10-07 | 2026-10-28 | 2026-10-07 | 2026-10-28 |  |  |  | Not Started | [8 empty] | Finalization of Interfaces with SE IT/OT Systems. Availability of DER Data.
DS(Batch 1) 6-GSS | Downstream | SLD and DB Validation Demo | 1 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 2026-07-12 | 100% | Completed
| Downstream | SLD and DB(Feeders of GSS Batch1) Feeders 120 (Graphic,Database,Link) | 11 | 2026-07-21 | 2026-08-02 | 2026-07-21 | 2026-08-02 | 2026-07-21 |  | 18% | In Progress | [8 empty] | Draft Man will mobilize on 7-Jul-26 | 3 |  |  | Total Expereienced Draftsmans - 1(Ma yucai) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI,Anas Bagadamah) | 11/DAY
| Downstream | SLD and DB Validation | 5 | 2026-08-03 | 2026-08-08 | 2026-08-03 | 2026-08-08 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 2) 9-GSS | Downstream | SLD and DB(Feeders of GSS Batch2) Feeders 180 (Graphic,Database,Link) | 5 | 2026-08-03 | 2026-08-08 | 2026-08-03 | 2026-08-08 |  |  |  | Not Started | [8 empty] | Draft Man will mobilize on 7-Jul-26 | 3 |  |  | Total Expereienced Draftsmans - 1(Ma yucai) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI,Anas Bagadamah) | 36/DAY
| Downstream | SLD and DB Validation | 5 | 2026-08-09 | 2026-08-13 | 2026-08-09 | 2026-08-13 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 3) 15-GSS | Downstream | SLD and DB(Feeders of GSS Batch3) Feeders 300 (Graphic,Database,Link) | 6 | 2026-08-09 | 2026-08-15 | 2026-08-09 | 2026-08-15 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 2(Ma yucai, Hu zhiyang) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI,Anas Bagadamah) | 50/DAY
| Downstream | SLD and DB Validation | 5 | 2026-08-16 | 2026-08-20 | 2026-08-16 | 2026-08-20 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 4) 15-GSS | Downstream | SLD and DB(Feeders of GSS Batch4) Feeders 300 (Graphic,Database,Link) | 6 | 2026-08-16 | 2026-08-22 | 2026-08-16 | 2026-08-22 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 2(Ma yucai, Hu zhiyang) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI,Anas Bagadamah) | 50/DAY
| Downstream | SLD and DB Validation | 5 | 2026-08-23 | 2026-08-27 | 2026-08-23 | 2026-08-27 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 5) 15-GSS | Downstream | SLD and DB(Feeders of GSS Batch5) Feeders 300 (Graphic,Database,Link) | 6 | 2026-08-23 | 2026-08-29 | 2026-08-23 | 2026-08-29 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 2(Ma yucai, Hu zhiyang) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI,Anas Bagadamah) | 50/DAY
| Downstream | SLD and DB Validation | 5 | 2026-08-30 | 2026-09-03 | 2026-08-30 | 2026-09-03 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 6) 15-GSS | Downstream | SLD and DB(Feeders of GSS Batch6) Feeders 300 (Graphic,Database,Link) | 6 | 2026-08-30 | 2026-09-05 | 2026-08-30 | 2026-09-05 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 2(Ma yucai, Hu zhiyang) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI,Anas Bagadamah) | 50/DAY
| Downstream | SLD and DB Validation | 5 | 2026-09-06 | 2026-09-10 | 2026-09-06 | 2026-09-10 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 7) 15-GSS | Downstream | SLD and DB(Feeders of GSS Batch7) Feeders 300 (Graphic,Database,Link) | 6 | 2026-09-06 | 2026-09-12 | 2026-09-06 | 2026-09-12 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 2(Ma yucai, Hu zhiyang) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI,Anas Bagadamah) | 50/DAY
| Downstream | SLD and DB Validation | 5 | 2026-09-13 | 2026-09-17 | 2026-09-13 | 2026-09-17 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 8) 15-GSS | Downstream | SLD and DB(Feeders of GSS Batch8) Feeders 300 (Graphic,Database,Link) | 6 | 2026-09-13 | 2026-09-19 | 2026-09-13 | 2026-09-19 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 2(Ma yucai, Hu zhiyang) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI,Anas Bagadamah) | 50/DAY
| Downstream | SLD and DB Validation | 5 | 2026-09-20 | 2026-09-24 | 2026-09-20 | 2026-09-24 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 9) 15-GSS | Downstream | SLD and DB(Feeders of GSS Batch9) Feeders 300 (Graphic,Database,Link) | 5 | 2026-09-20 | 2026-09-24 | 2026-09-20 | 2026-09-24 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 2(Ma yucai, Hu zhiyang) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI,Anas Bagadamah) | 60/DAY
| Downstream | SLD and DB Validation | 5 | 2026-09-26 | 2026-09-30 | 2026-09-26 | 2026-09-30 |  |  |  | Not Started | [9 empty] | 1
DS(Batch 10) 15-GSS | Downstream | SLD and DB(Feeders of GSS Batch10) Feeders 300 (Graphic,Database,Link) | 5 | 2026-09-26 | 2026-09-30 | 2026-09-26 | 2026-09-30 |  |  |  | Not Started | [9 empty] | 4 |  |  | Total Expereienced Draftsmans - 2(Ma yucai, Hu zhiyang) TOTAL SUPPORT DRAFTMAN -2(ALOGAIMI,Anas Bagadamah) | 60/DAY
| Downstream | SLD and DB Validation | 5 | 2026-10-01 | 2026-10-06 | 2026-10-01 | 2026-10-06 |  |  |  | Not Started | [9 empty] | 1
DS(E2E) | Downstream | E2E for SFD (Total 10423 8% For Testing 834) | 44 | 2026-08-08 | 2026-10-07 | 2026-08-08 | 2026-10-07 |  |  |  | Not Started | [8 empty] | Depend on STC TELECOME CIRCUITS READINESS(INSTALLATION, HARDWARE, SOFTWARE, CONFIGURATION, TRAFFIC, REROUTING,....ETC) Depend on Availability of SE Field Engineer Start the E2E test after the approval for the first downstream batch. E2E RMU Rate = 19 / Day | 2 |  |  | Leader - 1 (Wang yangyang) Support - 1 (Hu zhiyang) | 19/DAY
CUTOVER | Live On - Downstream | Cuttover | 2 | 2026-10-28 | 2026-10-31 | 2026-10-28 | 2026-10-31 |  |  |  | Not Started | [8 empty] | After STC Success E2E | 2 |  |  | Leader - 1 (Wang yangyang) Support - 1 (Hu zhiyang)
ADMS SAT | ADMS SAT | Hardware cybersecurity test | 2 | 2026-10-08 | 2026-10-11 | 2026-10-08 | 2026-10-11 |  |  |  | Not Started | [9 empty] | 3 |  |  | Team - 3 (Ma yucai, Sun zhongjie, Huzhiyang) Support -2 (Anas Bagadamah, Abdulrahman Gaees)
| ADMS SAT | Functional test - ADMS | 5 | 2026-10-12 | 2026-10-18 | 2026-10-12 | 2026-10-18 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Integration test | 5 | 2026-10-12 | 2026-10-18 | 2026-10-12 | 2026-10-18 |  |  |  | Not Started | [8 empty] | ADMS Integration Testing is dependent on the successful completion of all Phase 1 interface tests for the Centralized ESB. In accordance with the Local ESB schedule, the related integration preparation and coordination activities shall commence at least 45 days in advance. | 3
| ADMS SAT | Redundancy test | 2 | 2026-10-19 | 2026-10-20 | 2026-10-19 | 2026-10-20 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Stability | 3 | 2026-10-21 | 2026-10-25 | 2026-10-21 | 2026-10-25 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Regression test &unstructure test | 1 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-26 |  |  |  | Not Started | [9 empty] | 3
| ADMS SAT | Performance test | 1 | 2026-10-27 | 2026-10-27 | 2026-10-27 | 2026-10-27 |  |  |  | Not Started | [9 empty] | 3
Cyber Audit | Cyber Audit | Cyber Audit Phase1 | 16 | 2026-09-16 | 2026-10-07 | 2026-09-16 | 2026-10-07 |  |  |  | Not Started | [8 empty] | Cutover 1.Depend on the Approval for DTS-628 2.Depend on the telecom readiness
| Cyber Audit | Cyber Audit Phase2 | 20 | 2026-12-10 | 2027-01-06 | 2026-12-10 | 2027-01-06 |  |  |  | Not Started | [8 empty] | 1.Centralized Cybersecurity Audit 2.Depend on the SDCCs telecom readiness
Integration | Integration | DNMC Integration | 21 | 2026-10-02 | 2026-10-26 | 2026-10-02 | 2026-10-26 |  |  |  | Not Started | [8 empty] | 1.Depend on DNMC System Completed before 10 Aug, 2026 2.DNMC datapoint Scope to be confirmed by max 10, Aug 2026 3.DNMC <-----> DCC telecom completed by max 31 Aug, 2026 4.ICCP Configuration finished by 10 Aug, 2026 5.Testing（SDCC & DNMC ICCP Channel Testing,）finished by 20 Aug, 2026
| Integration | Local ESB SOFTWARE Installation | 9 | 2026-07-12 | 2026-07-21 | 2026-07-12 | 2026-07-21 | 2026-07-12 | 2026-07-18 | 100% | Completed | [8 empty] | SOFTWARE INSTALLATION
| Integration | DC-DR SYNC | 37 | 2026-10-15 | 2026-11-26 | 2026-10-15 | 2026-11-26 |  |  |  | Not Started | [8 empty] | Depend on availibility of LAN/WAN, to be10 - 12 weeks from design approval * TEMPRORY CONNECTION BETWEEN OT FW. TO MPLS CAN BE DONE TO ACHIVE THE SYCRONIZATION BETWEEN DC & DR
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26

## Summary Dates Option 01 &02 (2) (hidden)
| Western Rejion - Upstream | [11 empty] | Southern Rejion -Upstream
| Upstream Milstones |  |  |  | Upstream Milstones |  |  |  | Upstream Milstones |  |  |  | Upstream Milstones |  |  |  | Upstream Milstones
| MADINAH |  |  |  | JEDDAH |  |  |  | MAKKAH |  |  |  | ABHA |  |  |  | JIZAN
| E2E & Cutover (Grid SS) (Option 01) |  | Cutover Option 02 (Live on) |  | E2E & Cutover (Grid SS) (Option 01) |  | Cutover Option 02 (Live on) |  | E2E & Cutover (Grid SS) (Option 01) |  | Cutover Option 02 (Live on) |  | E2E & Cutover (Grid SS) (Option 01) |  | Cutover Option 02 (Live on) |  | E2E & Cutover (Grid SS) (Option 01) |  | Cutover Option 02 (Live on)
| Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates
Batch 01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2026-09-30 | 2026-10-08 | #REF! | #REF! | #REF! | 2026-10-08
Batch 02 | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
Batch 03 | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
Batch 04 | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
Batch 05 | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
Batch 06 | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF!
Batch 07 | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF!
Batch 08 | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF!
Batch 09 | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF!
Batch 10 | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF!