## MADINAH Migration Plan (hidden)
MADINAH Migration Flow | Activity | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Remark
| Database Migration (1st Round) (20-May-26) | [7 empty] | Madinah Database Migration (1st Round) completed
| SLD 1st patch (10 SS) | [7 empty] | SLD 1st patch in Madinah: (to be confirmed by CET)
| Validation by SE | [7 empty] | 3 days FF with SLD 1st patch
| E2E for 1st patch (10 SS - 20 points) | [7 empty] | Start 18-Jun Finish: 21-Jun Depend on Telecom Readiness
| SLD 2nd patch | [7 empty] | Start: 23-May Finish: 30-May
| SLD 3rd patch | [7 empty] | Start: 01-Jun Finish: 08-Jun
| SLD 4th patch | [7 empty] | Start: 01-Jun Finish: 08-Jun
| SLD 5th patch | [7 empty] | Start: 01-Jun Finish: 08-Jun
| SLD 6th patch | [7 empty] | Start: 09-Jun Finish: 16-Jun
| SLD 7th patch | [7 empty] | Start: 09-Jun Finish: 16-Jun
| SLD 8th patch | [7 empty] | Start: 09-Jun Finish: 16-Jun
| SLD 9th patch | [7 empty] | Start: 17-Jun Finish: 24-Jun
| SLD 10th patch | [7 empty] | Start: 24-Jul Finish: 30-Jul
| Final Validation by SE | [7 empty] | Start: 01-Aug Finish: 07-Aug E2E test shall be Finish to Finish +3 days with SLD
| Completion of E2E test | [7 empty] | shall be by mid of Aug-2026 (for Madinah)
| Alarm & Reporting Migration (14-Jun-26) | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability
| UI & Display Configuration (14-Jun-26) | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability
| Historian Migration (15-Aug-26) | [7 empty] | Depend on : *1st Round of Database Migration *Data Structure & Analysis from SE
| ADMS SAT | [7 empty] | Depend on : *Migration completion *80% of E2E testing
| Hardware cybersecurity test | [7 empty] | 3 days
| Functional test | [7 empty] | 5 days
| Performance test | [7 empty] | 3 days
| Integration test | [7 empty] | 2 days
| Redundancy test | [7 empty] | 2 days
| Stability & unstructure test | [7 empty] | 1 day
| Regression test | [7 empty] | 1 day
Training inside KSA
Training in China
| DERMS Software Installation shall start by 19-May-26 (Madinah) | [7 empty] | OT switches shall be mobilized by 16-May
DERMS SAT
Contract. TCC: 24-Jul-26
Variance:
- 6 Weeks

## Progress Summary
0% | Not Strated | Not Strated | SDCC - Overall Upstream Progress
50% | In Progress | In Progress
100% | Completed | Completed
MADINAH Upstream Progress | [7 empty] | JEDDAH Upstream Progress | [7 empty] | MAKKAH Upstream Progress
Batch No. | Planned % | Completed % | SLD Submission | SLD Validation | E2E for Grid SS | E2E Rectification | Cutover | Batch No. | Planned % | Completed % | SLD Submission | SLD Validation | E2E for Grid SS | E2E Rectification | Cutover | Batch No. | Planned % | Completed % | SLD Submission | SLD Validation | E2E for Grid SS | E2E Rectification | Cutover | -
Batch 01 | 0% | 20% | 100% | 0% | 0% | 0% | 0% | Batch 01 | 0% | 18% | 90% | 0% | 0% | 0% | 0% | Batch 01 | 0% | 18% | 90% | 0% | 0% | 0% | 0%
Batch 02 | 20% | 20% | 100% | 0% | 0% | 0% | 0% | Batch 02 | 0% | 18% | 90% | 0% | 0% | 0% | 0% | Batch 02 | 0% | 18% | 90% | 0% | 0% | 0% | 0%
Batch 03 | 20% | 18% | 90% | 0% | 0% | 0% | 0% | Batch 03 | 0% | 8.4% | 42% | 0% | 0% | 0% | 0% | Batch 03 | 0% | 18.6% | 93% | 0% | 0% | 0% | 0%
Batch 04 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 04 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 04 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 05 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 05 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 05 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 06 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 06 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 06 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 07 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 07 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 07 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 08 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 08 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 08 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 09 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 09 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 09 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 10 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 10 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Batch 10 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ABHA Upstream Progress | [15 empty] | JIZAN Upstream Progress
Batch No. | Planned % | Completed % | SLD Submission | SLD Validation | E2E for Grid SS | E2E Rectification | Cutover | [8 empty] | Batch No. | Planned % | Completed % | SLD Submission | SLD Validation | E2E for Grid SS | E2E Rectification | Cutover
Batch 01 | 40% | 30% | 100% | 50% | 0% | 0% | 0% | [8 empty] | Batch 01 | 40% | 30% | 100% | 50% | 0% | 0% | 0%
Batch 02 | 40% | 24% | 100% | 20% | 0% | 0% | 0% | [8 empty] | Batch 02 | 0% | 24% | 100% | 20% | 0% | 0% | 0%
Batch 03 | 20% | 20% | 100% | 0% | 0% | 0% | 0% | [8 empty] | Batch 03 | 20% | 18% | 90% | 0% | 0% | 0% | 0%
Batch 04 | 20% | 18% | 90% | 0% | 0% | 0% | 0% | [8 empty] | Batch 04 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 05 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 05 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 06 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 06 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 07 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 07 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Batch 08 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | Batch 08 | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Summary Dates Option 01 &02
| Western Region - Upstream | [5 empty] | Southern Region -Upstream
| MADINAH |  | JEDDAH |  | MAKKAH |  | ABHA |  | JIZAN
| E2E & Cutover (Grid SS) (Option 01) | Cutover Option 02 (Live on) | E2E & Cutover (Grid SS) (Option 01) | Cutover Option 02 (Live on) | E2E & Cutover (Grid SS) (Option 01) | Cutover Option 02 (Live on) | E2E & Cutover (Grid SS) (Option 01) | Cutover Option 02 (Live on) | E2E & Cutover (Grid SS) (Option 01) | Cutover Option 02 (Live on)
| Planned Finish Dates | Planned Finish Dates | Planned Finish Dates | Planned Finish Dates | Planned Finish Dates | Planned Finish Dates | Planned Finish Dates | Planned Finish Dates | Planned Finish Dates | Planned Finish Dates
Batch 01 | 2026-07-16 | 2026-09-15 | 2026-07-26 | 2026-10-25 | 2026-07-29 | 2026-10-07 | 2026-07-20 | 2026-09-15 | 2026-07-26 | 2026-09-15
Batch 02 | 2026-07-21 |  | 2026-08-02 | 2026-09-10 | 2026-08-03 | 2026-09-10 | 2026-07-26 |  | 2026-07-28
Batch 03 | 2026-07-29 |  | 2026-08-11 | 2026-09-07 | 2026-08-10 | 2026-09-07 | 2026-08-02 |  | 2026-08-04
Batch 04 | 2026-08-02 |  | 2026-08-20 | 2026-10-15 | 2026-08-17 | 2026-10-15 | 2026-08-10 |  | 2026-08-10
Batch 05 | 2026-08-06 |  | 2026-08-31 | 2026-10-04 | 2026-08-24 | 2026-10-04 | 2026-08-18 |  | 2026-08-16
Batch 06 | 2026-08-12 |  | 2026-09-10 |  | 2026-08-31 |  | 2026-08-25 |  | 2026-08-20
Batch 07 | 2026-08-18 |  | 2026-09-20 |  | 2026-09-07 |  | 2026-09-01 |  | 2026-08-26
Batch 08 | 2026-08-24 |  | 2026-09-29 |  | 2026-09-14 |  | 2026-09-08 |  | 2026-09-03
Batch 09 | 2026-08-30 |  | 2026-10-08 |  | 2026-09-21
Batch 10 | 2026-09-03 |  | 2026-10-20 |  | 2026-09-28

## ABHA Migration Plan
| Activity | Working Days | Planned Start | Planned Finish | Expected Start | Expected Finish | Actual Start / Expected Start | Actual Finish / Expected Finish | % Progress | Status | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Remark
| Database Migration (1st Round) |  |  | Completed |  | Completed |  |  | 100% | Completed | [7 empty] | Abha Database Migration (1st Round) completed
1st Batch (6 SS) | SLD and DB - Upstream | 19 | 2026-05-06 | 2026-06-02 | 2026-05-06 | 2026-06-02 | 2026-05-06 | 2026-06-02 | 100% | Completed | [8 empty] | 6 Days Calendar | SLD Submission | Batch 01 | 2026-05-24
| Validation by SE - Upstream | 19 | 2026-06-01 | 2026-06-22 | 2026-06-01 | 2026-06-22 | 2026-06-01 |  | 50% | Delayed | [8 empty] | 6 Days Calendar | SLD Validation | Batch 01 | 2026-05-25
| Telecom Rediness - Upstream |  | Started | 2026-07-14 | Started | 2026-07-14 |  |  |  | Not Started | [11 empty] | 2026-05-26
| E2E - Upstream | 2 | 2026-07-15 | 2026-07-16 | 2026-07-15 | 2026-07-16 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E | 5 Days Calendar | E2E for Grid SS | Batch 01 | 2026-05-27
| E2E Comments Rectification - Upstream | 2 | 2026-07-19 | 2026-07-20 | 2026-07-19 | 2026-07-20 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc | 5 Days Calendar | E2E Rectification | Batch 01 | 2026-05-28
| Cuttover - Upstream | 1 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 |  |  |  | Not Started | [8 empty] | 5 Days Calendar | Cutover | Batch 01 | 2026-05-29
2026-09-23
2nd Batch (10 SS) | SLD and DB - Upstream | 8 | 2026-05-22 | 2026-06-06 | 2026-05-22 | 2026-06-06 | 2026-05-22 | 2026-06-09 | 100% | Completed | [9 empty] | SLD Submission | Batch 02 | 2026-09-23
| Validation by SE - Upstream | 14 | 2026-06-10 | 2026-06-25 | 2026-06-10 | 2026-06-25 | 2026-06-14 |  | 20% | In Progress | [9 empty] | SLD Validation | Batch 02
| E2E - Upstream | 4 | 2026-07-19 | 2026-07-22 | 2026-07-19 | 2026-07-22 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 02
| E2E Comments Rectification - Upstream | 2 | 2026-07-23 | 2026-07-26 | 2026-07-23 | 2026-07-26 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 02
| Cuttover - Upstream | 1 | 2026-07-26 | 2026-07-26 | 2026-07-26 | 2026-07-26 |  |  |  | Not Started | [9 empty] | Cutover | Batch 02
3rd Batch (14 SS) | SLD and DB - Upstream | 10 | 2026-06-07 | 2026-06-17 | 2026-06-07 | 2026-06-17 | 2026-05-29 |  | 100% | Completed | [9 empty] | SLD Submission | Batch 03
| Validation by SE - Upstream | 5 | 2026-06-27 | 2026-07-01 | 2026-06-27 | 2026-07-01 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 03
| E2E - Upstream | 5 | 2026-07-23 | 2026-07-29 | 2026-07-23 | 2026-07-29 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 03
| E2E Comments Rectification - Upstream | 2 | 2026-07-30 | 2026-08-02 | 2026-07-30 | 2026-08-02 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 03
| Cuttover - Upstream | 1 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 2026-08-02 |  |  |  | Not Started | [9 empty] | Cutover | Batch 03
4th Batch (16 SS) | SLD and DB - Upstream | 7 | 2026-06-18 | 2026-06-25 | 2026-06-18 | 2026-06-25 |  |  | 90% | In Progress | [9 empty] | SLD Submission | Batch 04
| Validation by SE - Upstream | 5 | 2026-07-02 | 2026-07-07 | 2026-07-02 | 2026-07-07 |  |  |  | Not Started | [7 empty] | Patch will be Submitted partially to work in parallel |  | SLD Validation | Batch 04
| E2E - Upstream | 6 | 2026-07-30 | 2026-08-06 | 2026-07-30 | 2026-08-06 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 04
| E2E Comments Rectification - Upstream | 2 | 2026-08-09 | 2026-08-10 | 2026-08-09 | 2026-08-10 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 04
| Cuttover - Upstream | 1 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 |  |  |  | Not Started | [9 empty] | Cutover | Batch 04
5th Batch (16 SS) | SLD and DB - Upstream | 7 | 2026-06-27 | 2026-07-04 | 2026-06-27 | 2026-07-04 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 05
| Validation by SE - Upstream | 5 | 2026-07-08 | 2026-07-13 | 2026-07-08 | 2026-07-13 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 05
| E2E - Upstream | 6 | 2026-08-09 | 2026-08-16 | 2026-08-09 | 2026-08-16 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 05
| E2E Comments Rectification - Upstream | 2 | 2026-08-17 | 2026-08-18 | 2026-08-17 | 2026-08-18 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 05
| Cuttover - Upstream | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 |  |  |  | Not Started | [9 empty] | Cutover | Batch 05
6th Batch (14 SS) | SLD and DB - Upstream | 7 | 2026-07-05 | 2026-07-12 | 2026-07-05 | 2026-07-12 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 06
| Validation by SE - Upstream | 5 | 2026-07-14 | 2026-07-19 | 2026-07-14 | 2026-07-19 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 06
| E2E - Upstream | 5 | 2026-08-17 | 2026-08-23 | 2026-08-17 | 2026-08-23 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 06
| E2E Comments Rectification - Upstream | 2 | 2026-08-24 | 2026-08-25 | 2026-08-24 | 2026-08-25 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 06
| Cuttover - Upstream | 1 | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 |  |  |  | Not Started | [9 empty] | Cutover | Batch 06
7th Batch (15 SS) | SLD and DB - Upstream | 7 | 2026-07-13 | 2026-07-20 | 2026-07-13 | 2026-07-20 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 07
| Validation by SE - Upstream | 5 | 2026-07-21 | 2026-07-26 | 2026-07-21 | 2026-07-26 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 07
| E2E - Upstream | 5 | 2026-08-24 | 2026-08-30 | 2026-08-24 | 2026-08-30 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 07
| E2E Comments Rectification - Upstream | 2 | 2026-08-31 | 2026-09-01 | 2026-08-31 | 2026-09-01 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 07
| Cuttover - Upstream | 1 | 2026-09-01 | 2026-09-01 | 2026-09-01 | 2026-09-01 |  |  |  | Not Started | [9 empty] | Cutover | Batch 07
8th Batch (15 SS) | SLD and DB - Upstream | 7 | 2026-07-21 | 2026-07-28 | 2026-07-21 | 2026-07-28 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 08
| Validation by SE - Upstream | 4 | 2026-07-29 | 2026-08-02 | 2026-07-29 | 2026-08-02 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 08
| E2E - Upstream | 5 | 2026-08-31 | 2026-09-06 | 2026-08-31 | 2026-09-06 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 08
| E2E Comments Rectification - Upstream | 2 | 2026-09-07 | 2026-09-08 | 2026-09-07 | 2026-09-08 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 08
| Cuttover - Upstream | 1 | 2026-09-08 | 2026-09-08 | 2026-09-08 | 2026-09-08 |  |  |  | Not Started | [9 empty] | Cutover | Batch 08
Migration | Alarm & Reporting Migration | 19 | 2026-06-29 | 2026-07-20 | 2026-06-29 | 2026-07-20 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability | 6 Days Calendar
| UI & Display Configuration | 19 | 2026-06-29 | 2026-07-20 | 2026-06-29 | 2026-07-20 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability | 6 Days Calendar
| Historian Migration | 66 | 2026-06-29 | 2026-09-13 | 2026-06-29 | 2026-09-13 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Data Structure & Analysis from SE | 6 Days Calendar
Integration | DNMC Integration | 26 | 2026-09-09 | 2026-10-08 | 2026-09-09 | 2026-10-08 |  |  |  | Not Started | [7 empty] | 1.Depend on DNMC is Completed 2.DNMC datapoint Scope 3.DNMC <-----> DCC telecom completed 4.ICCP Configuration 5.Testing（SDCC & DNMC ICCP Channel Testing） 6.Batch 10 Cut Over Estimate add 5 days to do DNMC ICCP Intergration 7.Estimate all step Completed on 8th Sep
| Local ESB Installation | 7 | 2026-06-30 | 2026-07-07 | 2026-06-30 | 2026-07-07 |  |  |  | Not Started
| Central ESB Integration（Third Partly System Phase 1） | 167 | 2026-06-21 | 2026-12-31 | 2026-06-21 | 2026-12-31 |  |  |  | Delayed | [7 empty] | Details need be confirmed by SE and C-ESB side,under discussion. The relevant timeline can only be estimated as the following dependencies remain unconfirmed. 1.DEV timeline not be confirmed 2.Business flow not be confirmed between ADMS and TPS. 3.Interface not confimed because of the business flow. 4. Telecom condition timeline not be confirmed. 5.Detailed planned dates can not be clarified before the confirmation of the Change Order. 6.C-ESB hardware condition not be confirmed
| Central ESB Integration（Third Partly System Phase 2） | 129 | 2027-01-02 | 2027-05-31 | 2027-01-02 | 2027-05-31 |  |  |  | Not Started | [7 empty] | Details need be confirmed by SE and C-ESB side,under discussion. The relevant timeline can only be estimated as the following dependencies remain unconfirmed. 1.DEV timeline not be confirmed 2.Business flow not be confirmed between ADMS and TPS. 3.Interface not confimed because of the business flow. 4. Telecom condition timeline not be confirmed. 5.Detailed planned dates can not be clarified before the confirmation of the Change Order. 6.C-ESB hardware condition not be confirmed
| DC-DR SYNC | 18 | 2026-12-01 | 2026-12-21 | 2026-12-01 | 2026-12-21 |  |  |  | Not Started | [7 empty] | Depend on DC<---->DR Telecom Completed
Cut Over - Upstream (Live-On) | Cut Over（Batch 1:8） (2nd Option) | 3 | 2026-09-13 | 2026-09-15 | 2026-09-13 | 2026-09-15 |  |  |  | Not Started | [7 empty] | 1.Completed Cut Over(Upstream Batch1-10) 2.Completed SAT 3.Completed System Available Testing
ADMS SAT | Hardware cybersecurity test | 3 | 2026-08-26 | 2026-08-30 | 2026-08-26 | 2026-08-30 |  |  |  | Not Started | [8 empty] | 5 Days Calendar
| Functional test | 5 | 2026-08-31 | 2026-09-06 | 2026-08-31 | 2026-09-06 |  |  |  | Not Started | [8 empty] | 5 Days Calendar
| Redundancy test | 2 | 2026-09-07 | 2026-09-08 | 2026-09-07 | 2026-09-08 |  |  |  | Not Started | [8 empty] | 5 Days Calendar
| Stability & unstructure test | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 |  |  |  | Not Started | [8 empty] | 5 Days Calendar
| Regression test | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 |  |  |  | Not Started | [8 empty] | 5 Days Calendar
Training | Training inside KSA | 30 | 2026-08-01 | 2026-09-10 | 2026-08-01 | 2026-09-10 |  |  |  | Not Started | [7 empty] | on Job training to be conducted on each SDCC Training room to be ready by 8-Jun-26 | 5 Days Calendar
| Training in Factory | 29 | 2026-09-22 | 2026-11-02 | 2026-09-22 | 2026-11-02 |  |  |  | Not Started | [8 empty] | 5 Days Calendar
DERMS | DERMS Software Installation | 19 | 2026-07-14 | 2026-08-04 | 2026-06-14 | 2026-07-05 |  |  |  | Not Started | [7 empty] | The firewall configuration and required access rules shall be fully implemented and verified. Network access between the relevant systems and sites shall be available and confirmed. Connectivity between DC/DR shall be completed to support DC/DR communication and failover testing. All required ports, routing rules, and security policies shall be provided before testing. | 6 Days Calendar
| DERMS SAT | 11 | 2026-12-01 | 2026-12-15 | 2026-07-01 | 2026-07-15 |  |  |  | Not Started | [7 empty] | Data for DER is required from SE | 5 Days Calendar
Dowstream | SLD and DB ( Total 1,400) | 76 | 2026-09-09 | 2026-12-06 | 2026-09-09 | 2026-11-24 |  |  |  | Not Started
| Validation by SE | 76 | 2026-09-26 | 2026-12-22 | 2026-09-26 | 2026-12-10 |  |  |  | Not Started | [7 empty] | 3 days FF with SLD 1st patch
| E2E for SFD (10% - 1100) | 61 | 2026-10-01 | 2026-12-24 | 2026-10-01 | 2026-12-31 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness
| Cuttover | 1 | 2027-01-05 | 2027-01-05 | 2027-01-05 | 2027-01-05 |  |  |  | Not Started
Dowstream SAT | Functional test - ADMS | 5 | 2026-12-21 | 2026-12-27 | 2026-12-21 | 2026-12-27 |  |  |  | Not Started
| Integration test | 2 | 2026-12-28 | 2026-12-29 | 2026-12-28 | 2026-12-29 |  |  |  | Not Started
| Redundancy test | 2 | 2026-12-30 | 2026-12-31 | 2026-12-30 | 2026-12-31 |  |  |  | Not Started
| Stability & unstructure test | 1 | 2027-01-03 | 2027-01-03 | 2027-01-03 | 2027-01-03 |  |  |  | Not Started
| Regression test | 1 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 |  |  |  | Not Started
| Performance test | 3 | 2027-01-06 | 2027-01-10 | 2027-01-06 | 2027-01-10 |  |  |  | Not Started
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26

## MADINAH Migration Plan-
| Activity | Working Days | Planned Start | Planned Finish | Expected Start | Expected Finish | Actual Start / Expected Start | Actual Finish / Expected Finish | % Progress | Status | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Remark |  | 7 Days Claendar
| Downstream Database Migration (1st Round) |  |  | Completed |  | Completed |  |  | 100% | Completed | [9 empty] | 6 Days Calendar
1st Batch (6 SS) | SLD and DB Submission - Upstream | 19 | 2026-05-06 | 2026-06-02 | 2026-05-06 | 2026-06-02 | 2026-05-06 | 2026-05-21 | 100% | Completed | [9 empty] | 5 Days Calendar | SLD Submission | Batch 01 | 46166
| Validation by SE - Upstream | 7 | 2026-06-21 | 2026-06-28 | 2026-06-21 | 2026-06-28 |  |  |  | Delayed | [10 empty] | SLD Validation | Batch 01 | 46167
| Telecom Rediness - Upstream |  | Started | 2026-07-12 | Started | 2026-07-12 |  |  |  | Not Started | [12 empty] | 46168
| E2E - Upstream | 2 | 2026-07-13 | 2026-07-14 | 2026-07-13 | 2026-07-14 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  |  | E2E for Grid SS | Batch 01 | 46169
| E2E Comments Rectification - Upstream | 2 | 2026-07-15 | 2026-07-16 | 2026-07-15 | 2026-07-16 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  |  | E2E Rectification | Batch 01 | 46170
| Cuttover - Upstream (Option 1) | 1 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 |  |  |  | Not Started | [10 empty] | Cutover | Batch 01 | 46171
46288
2nd Batch (9 SS) | SLD and DB Submission - Upstream | 11 | 2026-05-22 | 2026-06-09 | 2026-05-22 | 2026-06-09 | 2026-05-22 | 2026-06-09 | 100% | Completed | [10 empty] | SLD Submission | Batch 02 | 46288
| Validation by SE - Upstream | 5 | 2026-06-29 | 2026-07-04 | 2026-06-29 | 2026-07-04 |  |  |  | Not Started | [10 empty] | SLD Validation | Batch 02
| E2E - Upstream | 3 | 2026-07-15 | 2026-07-19 | 2026-07-15 | 2026-07-19 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  |  | E2E for Grid SS | Batch 02
| E2E Comments Rectification - Upstream | 2 | 2026-07-20 | 2026-07-21 | 2026-07-20 | 2026-07-21 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  |  | E2E Rectification | Batch 02
| Cuttover - Upstream (Option 1) | 1 | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-21 |  |  |  | Not Started | [10 empty] | Cutover | Batch 02
3rd Batch (10 SS) | SLD and DB Submission - Upstream | 13 | 2026-06-10 | 2026-06-24 | 2026-06-10 | 2026-06-24 | 2026-05-29 |  | 90% | Delayed | [10 empty] | SLD Submission | Batch 03
| Validation by SE - Upstream | 5 | 2026-07-05 | 2026-07-09 | 2026-07-05 | 2026-07-09 |  |  |  | Not Started | [10 empty] | SLD Validation | Batch 03
| E2E - Upstream | 4 | 2026-07-20 | 2026-07-23 | 2026-07-20 | 2026-07-23 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  |  | E2E for Grid SS | Batch 03
| E2E Comments Rectification - Upstream | 4 | 2026-07-26 | 2026-07-29 | 2026-07-26 | 2026-07-29 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  |  | E2E Rectification | Batch 03
| Cuttover - Upstream (Option 1) | 1 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-29 |  |  |  | Not Started | [10 empty] | Cutover | Batch 03
4th Batch (11 SS) | SLD and DB Submission - Upstream | 7 | 2026-06-25 | 2026-07-02 | 2026-06-25 | 2026-07-02 |  |  |  | Delayed | [10 empty] | SLD Submission | Batch 04
| Validation by SE - Upstream | 5 | 2026-07-11 | 2026-07-15 | 2026-07-11 | 2026-07-15 |  |  |  | Not Started | [10 empty] | SLD Validation | Batch 04
| E2E - Upstream | 4 | 2026-07-26 | 2026-07-29 | 2026-07-26 | 2026-07-29 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  |  | E2E for Grid SS | Batch 04
| E2E Comments Rectification - Upstream | 2 | 2026-07-30 | 2026-08-02 | 2026-07-30 | 2026-08-02 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  |  | E2E Rectification | Batch 04
| Cuttover - Upstream (Option 1) | 1 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 2026-08-02 |  |  |  | Not Started | [10 empty] | Cutover | Batch 04
5th Batch (10 SS) | SLD and DB Submission - Upstream | 7 | 2026-07-04 | 2026-07-11 | 2026-07-04 | 2026-07-11 |  |  |  | Not Started | [10 empty] | SLD Submission | Batch 05
| Validation by SE - Upstream | 5 | 2026-07-16 | 2026-07-21 | 2026-07-16 | 2026-07-21 |  |  |  | Not Started | [10 empty] | SLD Validation | Batch 05
| E2E - Upstream | 4 | 2026-07-30 | 2026-08-04 | 2026-07-30 | 2026-08-04 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  |  | E2E for Grid SS | Batch 05
| E2E Comments Rectification - Upstream | 2 | 2026-08-05 | 2026-08-06 | 2026-08-05 | 2026-08-06 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  |  | E2E Rectification | Batch 05
| Cuttover - Upstream (Option 1) | 1 | 2026-08-06 | 2026-08-06 | 2026-08-06 | 2026-08-06 |  |  |  | Not Started | [10 empty] | Cutover | Batch 05
6th Batch (10 SS) | SLD and DB Submission - Upstream | 7 | 2026-07-12 | 2026-07-19 | 2026-07-12 | 2026-07-19 |  |  |  | Not Started | [10 empty] | SLD Submission | Batch 06
| Validation by SE - Upstream | 5 | 2026-07-22 | 2026-07-27 | 2026-07-22 | 2026-07-27 |  |  |  | Not Started | [10 empty] | SLD Validation | Batch 06
| E2E - Upstream | 4 | 2026-08-05 | 2026-08-10 | 2026-08-05 | 2026-08-10 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  |  | E2E for Grid SS | Batch 06
| E2E Comments Rectification - Upstream | 2 | 2026-08-11 | 2026-08-12 | 2026-08-11 | 2026-08-12 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  |  | E2E Rectification | Batch 06
| Cuttover - Upstream (Option 1) | 1 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 2026-08-12 |  |  |  | Not Started | [10 empty] | Cutover | Batch 06
7th Batch (10 SS) | SLD and DB Submission - Upstream | 7 | 2026-07-20 | 2026-07-27 | 2026-07-20 | 2026-07-27 |  |  |  | Not Started | [10 empty] | SLD Submission | Batch 07
| Validation by SE - Upstream | 5 | 2026-07-28 | 2026-08-02 | 2026-07-28 | 2026-08-02 |  |  |  | Not Started | [10 empty] | SLD Validation | Batch 07
| E2E - Upstream | 4 | 2026-08-11 | 2026-08-16 | 2026-08-11 | 2026-08-16 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  |  | E2E for Grid SS | Batch 07
| E2E Comments Rectification - Upstream | 2 | 2026-08-17 | 2026-08-18 | 2026-08-17 | 2026-08-18 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  |  | E2E Rectification | Batch 07
| Cuttover - Upstream (Option 1) | 1 | 2026-08-18 | 2026-08-18 | 2026-08-18 | 2026-08-18 |  |  |  | Not Started | [10 empty] | Cutover | Batch 07
8th Batch (10 SS) | SLD and DB Submission - Upstream | 7 | 2026-07-28 | 2026-08-04 | 2026-07-28 | 2026-08-04 |  |  |  | Not Started | [10 empty] | SLD Submission | Batch 08
| Validation by SE - Upstream | 5 | 2026-08-05 | 2026-08-10 | 2026-08-05 | 2026-08-10 |  |  |  | Not Started | [10 empty] | SLD Validation | Batch 08
| E2E - Upstream | 4 | 2026-08-17 | 2026-08-20 | 2026-08-17 | 2026-08-20 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  |  | E2E for Grid SS | Batch 08
| E2E Comments Rectification - Upstream | 2 | 2026-08-23 | 2026-08-24 | 2026-08-23 | 2026-08-24 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  |  | E2E Rectification | Batch 08
| Cuttover - Upstream (Option 1) | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 |  |  |  | Not Started | [10 empty] | Cutover | Batch 08
9th Batch (11 SS) | SLD and DB Submission - Upstream | 7 | 2026-08-05 | 2026-08-12 | 2026-08-05 | 2026-08-12 |  |  |  | Not Started | [10 empty] | SLD Submission | Batch 09
| Validation by SE - Upstream | 4 | 2026-08-13 | 2026-08-17 | 2026-08-13 | 2026-08-17 |  |  |  | Not Started | [10 empty] | SLD Validation | Batch 09
| E2E - Upstream | 4 | 2026-08-23 | 2026-08-26 | 2026-08-23 | 2026-08-26 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  |  | E2E for Grid SS | Batch 09
| E2E Comments Rectification - Upstream | 2 | 2026-08-27 | 2026-08-30 | 2026-08-27 | 2026-08-30 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  |  | E2E Rectification | Batch 09
| Cuttover - Upstream (Option 1) | 1 | 2026-08-30 | 2026-08-30 | 2026-08-30 | 2026-08-30 |  |  |  | Not Started | [10 empty] | Cutover | Batch 09
10th Batch (11 SS) | SLD and DB Submission - Upstream | 7 | 2026-08-13 | 2026-08-20 | 2026-08-13 | 2026-08-20 |  |  |  | Not Started | [10 empty] | SLD Submission | Batch 10
| Validation by SE - Upstream | 4 | 2026-08-22 | 2026-08-25 | 2026-08-22 | 2026-08-25 |  |  |  | Not Started | [10 empty] | SLD Validation | Batch 10
| E2E - Upstream | 4 | 2026-08-27 | 2026-09-01 | 2026-08-27 | 2026-09-01 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  |  | E2E for Grid SS | Batch 10
| E2E Comments Rectification - Upstream | 2 | 2026-09-02 | 2026-09-03 | 2026-09-02 | 2026-09-03 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  |  | E2E Rectification | Batch 10
| Cuttover - Upstream (Option 1) | 1 | 2026-09-03 | 2026-09-03 | 2026-09-03 | 2026-09-03 |  |  |  | Not Started | [10 empty] | Cutover | Batch 10
Migration | Alarm & Reporting Migration | 18 | 2026-06-29 | 2026-07-19 | 2026-06-29 | 2026-07-19 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability
| UI & Display Configuration | 18 | 2026-06-29 | 2026-07-19 | 2026-06-29 | 2026-07-19 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability
| Historian Migration | 65 | 2026-06-29 | 2026-09-12 | 2026-06-29 | 2026-09-12 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Data Structure & Analysis from SE
Integration | DNMC Integration | 26 | 2026-09-05 | 2026-10-05 | 2026-09-05 | 2026-10-05 |  |  |  | Not Started | [7 empty] | 1.Depend on DNMC is Completed 2.DNMC datapoint Scope 3.DNMC <-----> DCC telecom completed 4.ICCP Configuration 5.Testing（SDCC & DNMC ICCP Channel Testing） 6.Batch 10 Cut Over Estimate add 5 days to do DNMC ICCP Intergration 7.Estimate all step Completed on 8th Sep
| Local ESB Installation | 7 | 2026-06-30 | 2026-07-07 | 2026-06-30 | 2026-07-07 |  |  |  | Not Started
| Central ESB Integration（Third Partly System Phase 1） | 166 | 2026-06-21 | 2026-12-31 | 2026-06-21 | 2026-12-31 |  |  |  | Delayed | [7 empty] | Details need be confirmed by SE and C-ESB side,under discussion. The relevant timeline can only be estimated as the following dependencies remain unconfirmed. 1.DEV timeline not be confirmed 2.Business flow not be confirmed between ADMS and TPS. 3.Interface not confimed because of the business flow. 4. Telecom condition timeline not be confirmed. 5.Detailed planned dates can not be clarified before the confirmation of the Change Order. 6.C-ESB hardware condition not be confirmed
| Central ESB Integration（Third Partly System Phase 2） | 129 | 2027-01-02 | 2027-05-31 | 2027-01-02 | 2027-05-31 |  |  |  | Not Started | [7 empty] | Details need be confirmed by SE and C-ESB side,under discussion. The relevant timeline can only be estimated as the following dependencies remain unconfirmed. 1.DEV timeline not be confirmed 2.Business flow not be confirmed between ADMS and TPS. 3.Interface not confimed because of the business flow. 4. Telecom condition timeline not be confirmed. 5.Detailed planned dates can not be clarified before the confirmation of the Change Order. 6.C-ESB hardware condition not be confirmed
| DC-DR SYNC | 18 | 2026-12-01 | 2026-12-21 | 2026-12-01 | 2026-12-21 |  |  |  | Not Started | [7 empty] | Depend on DC<---->DR Telecom Completed Depend on Lan/Wan Delivery & Installation & TnC
Cut Over - Upstream (Live-On) | Cut Over（Batch 1:10） (2nd Option) | 3 | 2026-09-13 | 2026-09-15 | 2026-09-13 | 2026-09-15 |  |  |  | Not Started | [7 empty] | 1.Completed Cut Over(Upstream Batch1-10) 2.Completed SAT 3.Completed System Available Testing
ADMS SAT - Upstream | Hardware cybersecurity test | 3 | 2026-08-26 | 2026-08-30 | 2026-08-26 | 2026-08-30 |  |  |  | Not Started
| Functional test - SCADA | 5 | 2026-08-31 | 2026-09-06 | 2026-08-31 | 2026-09-06 |  |  |  | Not Started
| Redundancy test | 2 | 2026-09-07 | 2026-09-08 | 2026-09-07 | 2026-09-08 |  |  |  | Not Started | [8 empty] | 5 Days Calendar
| Stability & unstructure test | 1 | 2026-09-09 | 2026-09-09 | 2026-09-09 | 2026-09-09 |  |  |  | Not Started
| Regression test | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 |  |  |  | Not Started
Training | Training inside KSA | 30 | 2026-08-01 | 2026-09-10 | 2026-08-01 | 2026-09-10 |  |  |  | Not Started | [7 empty] | Depend on Training Room Rediness
| Training in Factory | 30 | 2026-09-22 | 2026-11-03 | 2026-09-22 | 2026-11-03 |  |  |  | Not Started
DERMS | DERMS Software Installation | 19 | 2026-07-28 | 2026-08-18 | 2026-06-14 | 2026-07-05 |  |  |  | Not Started | [7 empty] | The firewall configuration and required access rules shall be fully implemented and verified. Network access between the relevant systems and sites shall be available and confirmed. Connectivity between DC/DR shall be completed to support DC/DR communication and failover testing. All required ports, routing rules, and security policies shall be provided before testing.
| DERMS SAT | 12 | 2026-11-22 | 2026-12-07 | 2026-11-22 | 2026-12-07 |  |  |  | Not Started | [7 empty] | Data for DER is required from SE
Dowstream | SLD and DB ( Total 2,300) | 76 | 2026-09-05 | 2026-12-02 | 2026-09-05 | 2026-12-02 |  |  |  | Not Started
| Validation by SE | 76 | 2026-09-21 | 2026-12-19 | 2026-09-21 | 2026-12-19 |  |  |  | Not Started | [7 empty] | 3 days FF with SLD 1st patch
| E2E for SFD (10% - 1100) | 66 | 2026-09-28 | 2026-12-28 | 2026-09-28 | 2026-12-28 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness
| Cuttover | 1 | 2026-12-30 | 2026-12-30 | 2026-12-30 | 2026-12-30 |  |  |  | Not Started
Dowstream SAT | Functional test - ADMS | 5 | 2026-12-15 | 2026-12-21 | 2026-12-15 | 2026-12-21 |  |  |  | Not Started
| Integration test | 2 | 2026-12-22 | 2026-12-23 | 2026-12-22 | 2026-12-23 |  |  |  | Not Started
| Redundancy test | 2 | 2026-12-24 | 2026-12-27 | 2026-12-24 | 2026-12-27 |  |  |  | Not Started
| Stability & unstructure test | 1 | 2026-12-28 | 2026-12-28 | 2026-12-28 | 2026-12-28 |  |  |  | Not Started
| Regression test | 1 | 2026-12-29 | 2026-12-29 | 2026-12-29 | 2026-12-29 |  |  |  | Not Started
| Performance test | 3 | 2026-12-31 | 2027-01-04 | 2026-12-31 | 2027-01-04 |  |  |  | Not Started
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26

## Jizan Migration Plan
| Activity | Working Days | Planned Start | Planned Finish | Expected Start | Expected Finish | Actual Start / Expected Start | Actual Finish / Expected Finish | % Progress | Status | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Remark | 7 Days Claendar
| Database Migration (1st Round) (20-May-26) | [7 empty] | 100% | Completed | [7 empty] | Jizan Database Migration (1st Round) completed | 6 Days Calendar
1st Batch (7 SS) | SLD and DB - Upstream | 19 | 2026-05-06 | 2026-06-02 | 2026-05-06 | 2026-06-02 | 2026-05-06 | 2026-05-21 | 100% | Completed | [8 empty] | 5 Days Calendar | SLD Submission | Batch 01 |  | 46166
| Validation by SE - Upstream | 22 | 2026-06-01 | 2026-06-25 | 2026-06-01 | 2026-06-25 |  |  | 50% | In Progress | [9 empty] | SLD Validation | Batch 01 |  | 46167
| Telecom Rediness - Upstream |  | Started | 2026-07-19 | Started | 2026-07-19 |  |  |  | Not Started | [12 empty] | 46168
| E2E - Upstream | 3 | 2026-07-20 | 2026-07-22 | 2026-07-20 | 2026-07-22 |  |  |  | Not Started | [7 empty] | Grid Substation Depend on Telecom Readiness (24-Jun-26) Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 01 |  | 46169
| E2E Comments Rectification - Upstream | 2 | 2026-07-23 | 2026-07-26 | 2026-07-23 | 2026-07-26 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 01 |  | 46170
| Cuttover - Upstream | 1 | 2026-07-26 | 2026-07-26 | 2026-07-26 | 2026-07-26 |  |  |  | Not Started | [9 empty] | Cutover | Batch 01 |  | 46171
| - Upstream | [21 empty] | 46288
2nd Batch (6 SS) | SLD and DB - Upstream | 7 | 2026-06-03 | 2026-06-10 | 2026-06-03 | 2026-06-10 | 2026-05-22 | 2026-06-09 | 100% | Completed | [9 empty] | SLD Submission | Batch 02 |  | 46288
| Validation by SE - Upstream | 20 | 2026-06-10 | 2026-07-02 | 2026-06-10 | 2026-07-02 |  |  | 20% | In Progress | [9 empty] | SLD Validation | Batch 02
| E2E - Upstream | 2 | 2026-07-23 | 2026-07-26 | 2026-07-23 | 2026-07-26 |  |  |  | Not Started | [9 empty] | E2E for Grid SS | Batch 02
| E2E Comments Rectification - Upstream | 2 | 2026-07-27 | 2026-07-28 | 2026-07-27 | 2026-07-28 |  |  |  | Not Started | [9 empty] | E2E Rectification | Batch 02
| Cuttover - Upstream | 1 | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-28 |  |  |  | Not Started | [9 empty] | Cutover | Batch 02
- Upstream
3rd Batch (14 SS) | SLD and DB - Upstream | 13 | 2026-06-11 | 2026-06-25 | 2026-06-11 | 2026-06-25 | 2026-05-29 |  | 90% | In Progress | [9 empty] | SLD Submission | Batch 03
| Validation by SE - Upstream | 5 | 2026-07-04 | 2026-07-08 | 2026-07-04 | 2026-07-08 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 03
| E2E - Upstream | 5 | 2026-07-27 | 2026-08-02 | 2026-07-27 | 2026-08-02 |  |  |  | Not Started | [9 empty] | E2E for Grid SS | Batch 03
| E2E Comments Rectification - Upstream | 2 | 2026-08-03 | 2026-08-04 | 2026-08-03 | 2026-08-04 |  |  |  | Not Started | [9 empty] | E2E Rectification | Batch 03
| Cuttover - Upstream | 1 | 2026-08-04 | 2026-08-04 | 2026-08-04 | 2026-08-04 |  |  |  | Not Started | [9 empty] | Cutover | Batch 03
- Upstream
4th Batch (11 SS) | SLD and DB - Upstream | 7 | 2026-06-27 | 2026-07-04 | 2026-06-27 | 2026-07-04 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 04
| Validation by SE - Upstream | 5 | 2026-07-09 | 2026-07-14 | 2026-07-09 | 2026-07-14 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 04
| E2E - Upstream | 4 | 2026-08-03 | 2026-08-06 | 2026-08-03 | 2026-08-06 |  |  |  | Not Started | [9 empty] | E2E for Grid SS | Batch 04
| E2E Comments Rectification - Upstream | 2 | 2026-08-09 | 2026-08-10 | 2026-08-09 | 2026-08-10 |  |  |  | Not Started | [9 empty] | E2E Rectification | Batch 04
| Cuttover - Upstream | 1 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 |  |  |  | Not Started | [9 empty] | Cutover | Batch 04
- Upstream
5th Batch (11 SS) | SLD and DB - Upstream | 7 | 2026-07-05 | 2026-07-12 | 2026-07-05 | 2026-07-12 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 05
| Validation by SE - Upstream | 5 | 2026-07-15 | 2026-07-20 | 2026-07-15 | 2026-07-20 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 05
| E2E - Upstream | 4 | 2026-08-09 | 2026-08-12 | 2026-08-09 | 2026-08-12 |  |  |  | Not Started | [9 empty] | E2E for Grid SS | Batch 05
| E2E Comments Rectification - Upstream | 2 | 2026-08-13 | 2026-08-16 | 2026-08-13 | 2026-08-16 |  |  |  | Not Started | [9 empty] | E2E Rectification | Batch 05
| Cuttover - Upstream | 1 | 2026-08-16 | 2026-08-16 | 2026-08-16 | 2026-08-16 |  |  |  | Not Started | [9 empty] | Cutover | Batch 05
- Upstream
6th Batch (11 SS) | SLD and DB - Upstream | 7 | 2026-07-13 | 2026-07-20 | 2026-07-13 | 2026-07-20 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 06
| Validation by SE - Upstream | 5 | 2026-07-21 | 2026-07-26 | 2026-07-21 | 2026-07-26 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 06
| E2E - Upstream | 4 | 2026-08-13 | 2026-08-18 | 2026-08-13 | 2026-08-18 |  |  |  | Not Started | [9 empty] | E2E for Grid SS | Batch 06
| E2E Comments Rectification - Upstream | 2 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 |  |  |  | Not Started | [9 empty] | E2E Rectification | Batch 06
| Cuttover - Upstream | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 |  |  |  | Not Started | [9 empty] | Cutover | Batch 06
- Upstream
7th Batch (12 SS) | SLD and DB - Upstream | 7 | 2026-07-21 | 2026-07-28 | 2026-07-21 | 2026-07-28 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 07
| Validation by SE - Upstream | 5 | 2026-07-29 | 2026-08-03 | 2026-07-29 | 2026-08-03 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 07
| E2E - Upstream | 4 | 2026-08-19 | 2026-08-24 | 2026-08-19 | 2026-08-24 |  |  |  | Not Started | [9 empty] | E2E for Grid SS | Batch 07
| E2E Comments Rectification - Upstream | 2 | 2026-08-25 | 2026-08-26 | 2026-08-25 | 2026-08-26 |  |  |  | Not Started | [9 empty] | E2E Rectification | Batch 07
| Cuttover - Upstream | 1 | 2026-08-26 | 2026-08-26 | 2026-08-26 | 2026-08-26 |  |  |  | Not Started | [9 empty] | Cutover | Batch 07
- Upstream
8th Batch (13 SS) | SLD and DB - Upstream | 7 | 2026-07-29 | 2026-08-05 | 2026-07-29 | 2026-08-05 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 08
| Validation by SE - Upstream | 5 | 2026-08-06 | 2026-08-11 | 2026-08-06 | 2026-08-11 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 08
| E2E - Upstream | 6 | 2026-08-25 | 2026-09-01 | 2026-08-25 | 2026-09-01 |  |  |  | Not Started | [9 empty] | E2E for Grid SS | Batch 08
| E2E Comments Rectification - Upstream | 2 | 2026-09-02 | 2026-09-03 | 2026-09-02 | 2026-09-03 |  |  |  | Not Started | [9 empty] | E2E Rectification | Batch 08
| Cuttover - Upstream | 1 | 2026-09-03 | 2026-09-03 | 2026-09-03 | 2026-09-03 |  |  |  | Not Started | [9 empty] | Cutover | Batch 08
Migration | Alarm & Reporting Migration | 19 | 2026-06-29 | 2026-07-20 | 2026-06-29 | 2026-07-20 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability
| UI & Display Configuration | 19 | 2026-06-29 | 2026-07-20 | 2026-06-29 | 2026-07-20 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability
| Historian Migration | 66 | 2026-06-29 | 2026-09-13 | 2026-06-29 | 2026-09-13 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Data Structure & Analysis from SE
Integration | DNMC Integration | 26 | 2026-09-05 | 2026-10-04 | 2026-09-05 | 2026-10-04 | [11 empty] | 1.Depend on DNMC is Completed 2.DNMC datapoint Scope 3.DNMC <-----> DCC telecom completed 4.ICCP Configuration 5.Testing（SDCC & DNMC ICCP Channel Testing） 6.Batch 10 Cut Over Estimate add 5 days to do DNMC ICCP Intergration 7.Estimate all step Completed on 8th Sep
| Local ESB Installation | 7 | 2026-06-30 | 2026-07-07 | 2026-06-30 | 2026-07-07
| Central ESB Integration（Third Partly System Phase 1） | 167 | 2026-06-21 | 2026-12-31 | 2026-06-21 | 2026-12-31 | [11 empty] | Details need be confirmed by SE and C-ESB side,under discussion. The relevant timeline can only be estimated as the following dependencies remain unconfirmed. 1.DEV timeline not be confirmed 2.Business flow not be confirmed between ADMS and TPS. 3.Interface not confimed because of the business flow. 4. Telecom condition timeline not be confirmed. 5.Detailed planned dates can not be clarified before the confirmation of the Change Order. 6.C-ESB hardware condition not be confirmed
| Central ESB Integration（Third Partly System Phase 2） | 129 | 2027-01-02 | 2027-05-31 | 2027-01-02 | 2027-05-31 | [11 empty] | Details need be confirmed by SE and C-ESB side,under discussion. The relevant timeline can only be estimated as the following dependencies remain unconfirmed. 1.DEV timeline not be confirmed 2.Business flow not be confirmed between ADMS and TPS. 3.Interface not confimed because of the business flow. 4. Telecom condition timeline not be confirmed. 5.Detailed planned dates can not be clarified before the confirmation of the Change Order. 6.C-ESB hardware condition not be confirmed |  |  |  | `
| DC-DR SYNC | 18 | 2026-12-01 | 2026-12-21 | 2026-12-01 | 2026-12-21 | [11 empty] | Depend on DC<---->DR Telecom Completed
Cut Over - Upstream (Live-On) | Cut Over（Batch1-8） | 3 | 2026-09-13 | 2026-09-15 | 2026-09-13 | 2026-09-15 |  |  |  | Not Started | [7 empty] | 1.Completed Cut Over(Upstream Batch1-10) 2.Completed SAT 3.Completed System Available Testing
ADMS SAT | Hardware cybersecurity test | 3 | 2026-08-23 | 2026-08-25 | 2026-08-23 | 2026-08-25 |  |  |  | Not Started
| Functional test | 5 | 2026-08-26 | 2026-09-01 | 2026-08-26 | 2026-09-01 |  |  |  | Not Started
| Redundancy test | 2 | 2026-09-02 | 2026-09-03 | 2026-09-02 | 2026-09-03 |  |  |  | Not Started
| Stability & unstructure test | 1 | 2026-09-06 | 2026-09-06 | 2026-09-06 | 2026-09-06 |  |  |  | Not Started
| Regression test | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 |  |  |  | Not Started
Training | Training inside KSA | 30 | 2026-08-01 | 2026-09-10 | 2026-08-01 | 2026-09-10 |  |  |  | Not Started
| Training in Factory | 29 | 2026-09-22 | 2026-11-02 | 2026-09-22 | 2026-11-02 |  |  |  | Not Started
DERMS | DERMS Software Installation | 19 | 2026-07-14 | 2026-08-04 | 2026-06-01 | 2026-06-22 |  |  |  | Not Started | [7 empty] | The firewall configuration and required access rules shall be fully implemented and verified. Network access between the relevant systems and sites shall be available and confirmed. Connectivity between DC/DR shall be completed to support DC/DR communication and failover testing. All required ports, routing rules, and security policies shall be provided before testing.
| DERMS SAT | 11 | 2026-11-23 | 2026-12-07 | 2026-07-01 | 2026-07-15 |  |  |  | Not Started | [7 empty] | Data for DER is required from SE
Dowstream | SLD and DB ( Total 1,100) | 86 | 2026-09-05 | 2026-12-13 | 2026-09-05 | 2026-12-13 |  |  |  | Not Started
| Validation by SE | 86 | 2026-09-21 | 2026-12-29 | 2026-09-21 | 2026-12-29 |  |  |  | Not Started | [7 empty] | 3 days FF with SLD 1st patch
| E2E for SFD (10% - 1100) | 71 | 2026-09-28 | 2027-01-04 | 2026-09-28 | 2026-12-28 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness
| Cuttover | 1 | 2027-01-05 | 2027-01-05 | 2027-01-12 | 2027-01-12 |  |  |  | Not Started
Dowstream SAT | Functional test - ADMS | 5 | 2026-12-16 | 2026-12-22 | 2026-12-23 | 2026-12-29 |  |  |  | Not Started
| Integration test | 2 | 2026-12-23 | 2026-12-24 | 2026-12-30 | 2027-01-03 |  |  |  | Not Started
| Redundancy test | 2 | 2026-12-27 | 2026-12-28 | 2027-01-04 | 2027-01-05 |  |  |  | Not Started
| Stability & unstructure test | 1 | 2026-12-29 | 2026-12-29 | 2027-01-06 | 2027-01-07 |  |  |  | Not Started
| Regression test | 1 | 2026-12-30 | 2026-12-30 | 2027-01-10 | 2027-01-10 |  |  |  | Not Started
| Performance test | 3 | 2027-01-06 | 2027-01-10 | 2027-01-11 | 2027-01-11 |  |  |  | Not Started
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26

## Jeddah Migration Plan
| Activity | Working Days | Planned Start | Planned Finish | Expected Start | Expected Finish | Actual Start / Expected Start | Actual Finish / Expected Finish | % Progress | Status | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Remark | 7 Days Claendar
| Database Migration for Upstream (1st Round) |  | 2026-05-18 | 2026-05-30 | 2026-05-18 | 2026-05-30 |  |  | 100% | Completed | [7 empty] | Makkah Database Migration (1st Round) in progress | 6 Days Calendar
1st Batch (7 SS) | SLD and DB - Upstream | 29 | 2026-05-31 | 2026-07-02 | 2026-05-31 | 2026-07-02 | 2026-05-06 |  | 90% | In Progress | [8 empty] | 5 Days Calendar | SLD Submission | Batch 01 | 2026-05-24
| Software Installation | 17 | 2026-06-13 | 2026-07-01 | 2026-06-13 | 2026-07-01 |  |  | 30% | In Progress | [11 empty] | 2026-05-25
| Configuration of Network & Cyber Security | 15 | 2026-07-02 | 2026-07-19 | 2026-07-02 | 2026-07-19 |  |  |  | Not Started
| Validation by SE - Upstream | 11 | 2026-07-04 | 2026-07-15 | 2026-07-04 | 2026-07-15 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 01 | 2026-05-26
| Telecom Rediness - Upstream |  | Started | 2026-07-09 | Started | 2026-07-09 |  |  |  | Not Started | [11 empty] | 2026-05-27
| E2E - Upstream | 3 | 2026-07-20 | 2026-07-22 | 2026-07-20 | 2026-07-22 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 01 | 2026-05-28
| E2E Comments Rectification - Upstream | 2 | 2026-07-23 | 2026-07-26 | 2026-07-23 | 2026-07-26 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 01 | 2026-05-29
| Cuttover - Upstream | 1 | 2026-07-26 | 2026-07-26 | 2026-07-26 | 2026-07-26 |  |  |  | Not Started | [9 empty] | Cutover | Batch 01 | 2026-09-23
| - Upstream | [19 empty] | Batch 02 | 2026-09-23
2nd Batch (15 SS) | SLD and DB - Upstream | 4 | 2026-07-04 | 2026-07-07 | 2026-07-04 | 2026-07-07 | 2026-05-22 |  | 90% | In Progress | [9 empty] | SLD Submission | Batch 02
| Validation by SE - Upstream | 5 | 2026-07-16 | 2026-07-21 | 2026-07-16 | 2026-07-21 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 02
| E2E - Upstream | 5 | 2026-07-23 | 2026-07-29 | 2026-07-23 | 2026-07-29 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 02
| E2E Comments Rectification - Upstream | 2 | 2026-07-30 | 2026-08-02 | 2026-07-30 | 2026-08-02 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 02
| Cuttover - Upstream | 1 | 2026-08-02 | 2026-08-02 | 2026-08-02 | 2026-08-02 |  |  |  | Not Started | [9 empty] | Cutover | Batch 02
| - Upstream | [19 empty] | Batch 03
3rd Batch (19 SS) | SLD and DB - Upstream | 4 | 2026-07-08 | 2026-07-12 | 2026-07-08 | 2026-07-12 | 2026-05-29 |  | 42% | In Progress | [9 empty] | SLD Submission | Batch 03
| Validation by SE - Upstream | 5 | 2026-07-22 | 2026-07-27 | 2026-07-22 | 2026-07-27 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 03
| E2E - Upstream | 7 | 2026-07-30 | 2026-08-09 | 2026-07-30 | 2026-08-09 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 03
| E2E Comments Rectification - Upstream | 2 | 2026-08-10 | 2026-08-11 | 2026-08-10 | 2026-08-11 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 03
| Cuttover - Upstream | 1 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 |  |  |  | Not Started | [9 empty] | Cutover | Batch 03
| - Upstream | [19 empty] | Batch 04
4th Batch (20 SS) | SLD and DB - Upstream | 7 | 2026-07-13 | 2026-07-20 | 2026-07-13 | 2026-07-20 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 04
| Validation by SE - Upstream | 5 | 2026-07-28 | 2026-08-02 | 2026-07-28 | 2026-08-02 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 04
| E2E - Upstream | 7 | 2026-08-10 | 2026-08-18 | 2026-08-10 | 2026-08-18 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 04
| E2E Comments Rectification - Upstream | 2 | 2026-08-19 | 2026-08-20 | 2026-08-19 | 2026-08-20 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 04
| Cuttover - Upstream | 1 | 2026-08-20 | 2026-08-20 | 2026-08-20 | 2026-08-20 |  |  |  | Not Started | [9 empty] | Cutover | Batch 04
| - Upstream | [19 empty] | Batch 05
5th Batch (19 SS) | SLD and DB - Upstream | 7 | 2026-07-21 | 2026-07-28 | 2026-07-21 | 2026-07-28 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 05
| Validation by SE - Upstream | 5 | 2026-08-03 | 2026-08-08 | 2026-08-03 | 2026-08-08 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 05
| E2E - Upstream | 7 | 2026-08-19 | 2026-08-27 | 2026-08-19 | 2026-08-27 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 05
| E2E Comments Rectification - Upstream | 2 | 2026-08-30 | 2026-08-31 | 2026-08-30 | 2026-08-31 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 05
| Cuttover - Upstream | 1 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31 |  |  |  | Not Started | [9 empty] | Cutover | Batch 05
| - Upstream | [19 empty] | Batch 06
6th Batch (22 SS) | SLD and DB - Upstream | 7 | 2026-07-29 | 2026-08-05 | 2026-07-29 | 2026-08-05 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 06
| Validation by SE - Upstream | 5 | 2026-08-09 | 2026-08-13 | 2026-08-09 | 2026-08-13 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 06
| E2E - Upstream | 8 | 2026-08-30 | 2026-09-08 | 2026-08-30 | 2026-09-08 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 06
| E2E Comments Rectification - Upstream | 2 | 2026-09-09 | 2026-09-10 | 2026-09-09 | 2026-09-10 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 06
| Cuttover - Upstream | 1 | 2026-09-10 | 2026-09-10 | 2026-09-10 | 2026-09-10 |  |  |  | Not Started | [9 empty] | Cutover | Batch 06
| - Upstream | [19 empty] | Batch 07
7th Batch (17 SS) | SLD and DB - Upstream | 7 | 2026-08-06 | 2026-08-13 | 2026-08-06 | 2026-08-13 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 07
| Validation by SE - Upstream | 5 | 2026-08-15 | 2026-08-19 | 2026-08-15 | 2026-08-19 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 07
| E2E - Upstream | 6 | 2026-09-09 | 2026-09-16 | 2026-09-09 | 2026-09-16 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 07
| E2E Comments Rectification - Upstream | 2 | 2026-09-17 | 2026-09-20 | 2026-09-17 | 2026-09-20 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 07
| Cuttover - Upstream | 1 | 2026-09-20 | 2026-09-20 | 2026-09-20 | 2026-09-20 |  |  |  | Not Started | [9 empty] | Cutover | Batch 07
| - Upstream | [19 empty] | Batch 08
8th Batch (20 SS) | SLD and DB - Upstream | 7 | 2026-08-15 | 2026-08-22 | 2026-08-15 | 2026-08-22 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 08
| Validation by SE - Upstream | 5 | 2026-08-23 | 2026-08-27 | 2026-08-23 | 2026-08-27 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 08
| E2E - Upstream | 6 | 2026-09-17 | 2026-09-27 | 2026-09-17 | 2026-09-27 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 08
| E2E Comments Rectification - Upstream | 2 | 2026-09-28 | 2026-09-29 | 2026-09-28 | 2026-09-29 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 08
| Cuttover - Upstream | 1 | 2026-09-29 | 2026-09-29 | 2026-09-29 | 2026-09-29 |  |  |  | Not Started | [9 empty] | Cutover | Batch 08
| - Upstream | [19 empty] | Batch 09
9th Batch (19 SS) | SLD and DB - Upstream | 7 | 2026-08-23 | 2026-08-30 | 2026-08-23 | 2026-08-30 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 09
| Validation by SE - Upstream | 5 | 2026-09-01 | 2026-09-06 | 2026-09-01 | 2026-09-06 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 09
| E2E - Upstream | 7 | 2026-09-28 | 2026-10-06 | 2026-09-28 | 2026-10-06 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 09
| E2E Comments Rectification - Upstream | 2 | 2026-10-07 | 2026-10-08 | 2026-10-07 | 2026-10-08 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 09
| Cuttover - Upstream | 1 | 2026-10-08 | 2026-10-08 | 2026-10-08 | 2026-10-08 |  |  |  | Not Started | [9 empty] | Cutover | Batch 09
| - Upstream | [19 empty] | Batch 10
10th Batch (22 SS) | SLD and DB - Upstream | 7 | 2026-08-31 | 2026-09-07 | 2026-08-31 | 2026-09-07 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 10
| Validation by SE - Upstream | 5 | 2026-09-08 | 2026-09-13 | 2026-09-08 | 2026-09-13 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 10
| E2E - Upstream | 8 | 2026-10-07 | 2026-10-18 | 2026-10-07 | 2026-10-18 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 10
| E2E Comments Rectification - Upstream | 2 | 2026-10-19 | 2026-10-20 | 2026-10-19 | 2026-10-20 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 10
| Cuttover - Upstream | 1 | 2026-10-20 | 2026-10-20 | 2026-10-20 | 2026-10-20 |  |  |  | Not Started | [9 empty] | Cutover | Batch 10
- Upstream
Migration | Alarm & Reporting Migration | 18 | 2026-07-16 | 2026-08-05 | 2026-07-16 | 2026-08-05 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability *Software Completion
| UI & Display Configuration | 18 | 2026-07-16 | 2026-08-05 | 2026-07-16 | 2026-08-05 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability
| Historian Migration | 65 | 2026-07-16 | 2026-09-29 | 2026-07-16 | 2026-09-29 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Data Structure & Analysis from SE
Integration | DNMC Integration | 26 | 2026-10-21 | 2026-11-19 | 2026-10-21 | 2026-11-19 | [11 empty] | 1.Depend on DNMC is Completed 2.DNMC datapoint Scope 3.DNMC <-----> DCC telecom completed 4.ICCP Configuration 5.Testing（SDCC & DNMC ICCP Channel Testing） 6.Batch 10 Cut Over Estimate add 5 days to do DNMC ICCP Intergration 7.Estimate all step Completed on 8th Sep
| Local ESB Installation | 7 | 2026-06-30 | 2026-07-07 | 2026-06-30 | 2026-07-07
| Central ESB Integration（Third Partly System Phase 1） | 167 | 2026-06-21 | 2026-12-31 | 2026-06-21 | 2026-12-31 | [11 empty] | Details need be confirmed by SE and C-ESB side,under discussion. The relevant timeline can only be estimated as the following dependencies remain unconfirmed. 1.DEV timeline not be confirmed 2.Business flow not be confirmed between ADMS and TPS. 3.Interface not confimed because of the business flow. 4. Telecom condition timeline not be confirmed. 5.Detailed planned dates can not be clarified before the confirmation of the Change Order. 6.C-ESB hardware condition not be confirmed
| Central ESB Integration（Third Partly System Phase 2） | 129 | 2027-01-02 | 2027-05-31 | 2027-01-02 | 2027-05-31 | [11 empty] | Details need be confirmed by SE and C-ESB side,under discussion. The relevant timeline can only be estimated as the following dependencies remain unconfirmed. 1.DEV timeline not be confirmed 2.Business flow not be confirmed between ADMS and TPS. 3.Interface not confimed because of the business flow. 4. Telecom condition timeline not be confirmed. 5.Detailed planned dates can not be clarified before the confirmation of the Change Order. 6.C-ESB hardware condition not be confirmed
| DC-DR SYNC | 18 | 2026-12-01 | 2026-12-21 | 2026-12-01 | 2026-12-21 | [11 empty] | Depend on DC<---->DR Telecom Completed
Cut Over - Upstream (Live-On) | Cut Over（Batch1-10） | 3 | 2026-10-21 | 2026-10-25 | 2026-10-21 | 2026-10-25 |  |  |  | Not Started | [7 empty] | 1.Completed Cut Over(Upstream Batch1-10) 2.Completed SAT 3.Completed System Available Testing
ADMS SAT | Hardware cybersecurity test | 3 | 2026-09-30 | 2026-10-04 | 2026-09-30 | 2026-10-04 |  |  |  | Not Started
| Functional test | 5 | 2026-10-05 | 2026-10-11 | 2026-10-05 | 2026-10-11 |  |  |  | Not Started
| Redundancy test | 2 | 2026-10-12 | 2026-10-13 | 2026-10-12 | 2026-10-13 |  |  |  | Not Started
| Stability & unstructure test | 1 | 2026-10-14 | 2026-10-14 | 2026-10-14 | 2026-10-14 |  |  |  | Not Started
| Regression test | 1 | 2026-10-15 | 2026-10-15 | 2026-10-15 | 2026-10-15 |  |  |  | Not Started
Training | Training inside KSA | 30 | 2026-08-01 | 2026-09-10 | 2026-08-01 | 2026-09-10 |  |  |  | Not Started | [7 empty] | depend on Training Room Rediness
| Training in Factory | 30 | 2026-11-01 | 2026-12-10 | 2026-11-01 | 2026-12-10 |  |  |  | Not Started | [7 empty] | no resource avaialble , depend on finalizeatoion Cutover
DERMS | DERMS Software Installation | 18 | 2026-09-05 | 2026-09-26 | 2026-07-23 | 2026-08-13 |  |  |  | Not Started | [7 empty] | The firewall configuration and required access rules shall be fully implemented and verified. Network access between the relevant systems and sites shall be available and confirmed. Connectivity between DC/DR shall be completed to support DC/DR communication and failover testing. All required ports, routing rules, and security policies shall be provided before testing.
| DERMS SAT | 10 | 2027-01-08 | 2027-01-22 | 2026-08-14 | 2026-08-28 |  |  |  | Not Started | [7 empty] | Data for DER is required from SE
Dowstream | SLD and DB ( Total 4,000) | 101 | 2026-10-21 | 2027-02-15 | 2026-10-21 | 2027-02-15 |  |  |  | Not Started
| Validation by SE | 101 | 2026-11-07 | 2027-03-03 | 2026-11-07 | 2027-03-03 |  |  |  | Not Started | [7 empty] | 3 days FF with SLD 1st patch
| E2E for SFD (10% - 1800) | 66 | 2026-11-12 | 2027-02-11 | 2026-11-12 | 2027-02-11 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness
| Cuttover | 1 | 2027-02-15 | 2027-02-15 | 2027-02-15 | 2027-02-15 |  |  |  | Not Started
Dowstream SAT | Functional test - ADMS | 5 | 2027-01-31 | 2027-02-04 | 2027-01-31 | 2027-02-04 |  |  |  | Not Started
| Integration test | 2 | 2027-02-07 | 2027-02-08 | 2027-02-07 | 2027-02-08 |  |  |  | Not Started
| Redundancy test | 2 | 2027-02-09 | 2027-02-10 | 2027-02-09 | 2027-02-10 |  |  |  | Not Started
| Stability & unstructure test | 1 | 2027-02-11 | 2027-02-11 | 2027-02-11 | 2027-02-11 |  |  |  | Not Started
| Regression test | 1 | 2027-02-14 | 2027-02-14 | 2027-02-14 | 2027-02-14 |  |  |  | Not Started
| Performance test | 3 | 2027-02-16 | 2027-02-18 | 2027-02-16 | 2027-02-18 |  |  |  | Not Started
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26

## Makkah Migration Plan
| Activity | Working Days | Planned Start | Planned Finish | Expected Start | Expected Finish | Actual Start / Expected Start | Actual Finish / Expected Finish | % Progress | Status | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | Remark | 7 Days Claendar
| Database Migration (1st Round) |  | 2026-05-06 | 2026-05-21 | 2026-05-06 | 2026-05-21 |  |  | 100% | Completed | [7 empty] | Makkah Database Migration (1st Round) in progress | 6 Days Calendar
1st Batch (6 SS) | SLD and DB - Upstream | 33 | 2026-05-31 | 2026-07-07 | 2026-05-31 | 2026-07-07 | 2026-05-06 |  | 90% | In Progress | [8 empty] | 5 Days Calendar | SLD Submission | Batch 01 | 2026-05-24
| Software Installation | 14 | 2026-06-21 | 2026-07-06 | 2026-06-21 | 2026-07-06 |  |  | 50% | In Progress
| Configuration of Network & Cyber Security | 15 | 2026-07-07 | 2026-07-23 | 2026-07-07 | 2026-07-23 |  |  |  | Not Started
| Validation by SE - Upstream | 10 | 2026-07-08 | 2026-07-19 | 2026-07-08 | 2026-07-19 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 01 | 2026-05-25
| Telecom Rediness - Upstream |  | Started | 2026-06-28 | Started | 2026-06-28 |  |  |  | Not Started | [11 empty] | 2026-05-26
| E2E - Upstream | 2 | 2026-07-26 | 2026-07-27 | 2026-07-26 | 2026-07-27 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 01 | 2026-05-27
| E2E Comments Rectification - Upstream | 2 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 01 | 2026-05-28
| Cuttover - Upstream | 1 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-29 |  |  |  | Not Started | [9 empty] | Cutover | Batch 01 | 2026-05-29
| - Upstream | [19 empty] | Batch 02 | 2026-09-23
2nd Batch (9 SS) | SLD and DB - Upstream | 22 | 2026-06-16 | 2026-07-11 | 2026-06-16 | 2026-07-11 | 2026-05-22 |  | 90% | In Progress | [9 empty] | SLD Submission | Batch 02 | 46288
| Validation by SE - Upstream | 5 | 2026-07-20 | 2026-07-25 | 2026-07-20 | 2026-07-25 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 02
| E2E - Upstream | 3 | 2026-07-28 | 2026-07-30 | 2026-07-28 | 2026-07-30 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 02
| E2E Comments Rectification - Upstream | 2 | 2026-08-02 | 2026-08-03 | 2026-08-02 | 2026-08-03 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 02
| Cuttover - Upstream | 1 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 |  |  |  | Not Started | [9 empty] | Cutover | Batch 02
| - Upstream | [19 empty] | Batch 03
3rd Batch (15 SS) | SLD and DB - Upstream | 4 | 2026-07-12 | 2026-07-15 | 2026-07-12 | 2026-07-15 | 2026-05-29 |  | 93% | In Progress | [9 empty] | SLD Submission | Batch 03
| Validation by SE - Upstream | 4 | 2026-07-26 | 2026-07-29 | 2026-07-26 | 2026-07-29 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 03
| E2E - Upstream | 5 | 2026-08-02 | 2026-08-06 | 2026-08-02 | 2026-08-06 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 03
| E2E Comments Rectification - Upstream | 2 | 2026-08-09 | 2026-08-10 | 2026-08-09 | 2026-08-10 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 03
| Cuttover - Upstream | 1 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 |  |  |  | Not Started | [9 empty] | Cutover | Batch 03
| - Upstream | [19 empty] | Batch 04
4th Batch (15 SS) | SLD and DB - Upstream | 7 | 2026-07-16 | 2026-07-23 | 2026-07-16 | 2026-07-23 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 04
| Validation by SE - Upstream | 5 | 2026-07-30 | 2026-08-04 | 2026-07-30 | 2026-08-04 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 04
| E2E - Upstream | 5 | 2026-08-09 | 2026-08-13 | 2026-08-09 | 2026-08-13 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 04
| E2E Comments Rectification - Upstream | 2 | 2026-08-16 | 2026-08-17 | 2026-08-16 | 2026-08-17 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 04
| Cuttover - Upstream | 1 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 |  |  |  | Not Started | [9 empty] | Cutover | Batch 04
| - Upstream | [19 empty] | Batch 05
5th Batch (15 SS) | SLD and DB - Upstream | 7 | 2026-07-25 | 2026-08-01 | 2026-07-25 | 2026-08-01 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 05
| Validation by SE - Upstream | 5 | 2026-08-05 | 2026-08-10 | 2026-08-05 | 2026-08-10 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 05
| E2E - Upstream | 5 | 2026-08-16 | 2026-08-20 | 2026-08-16 | 2026-08-20 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 05
| E2E Comments Rectification - Upstream | 2 | 2026-08-23 | 2026-08-24 | 2026-08-23 | 2026-08-24 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 05
| Cuttover - Upstream | 1 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 |  |  |  | Not Started | [9 empty] | Cutover | Batch 05
| - Upstream | [19 empty] | Batch 06
6th Batch (15 SS) | SLD and DB - Upstream | 7 | 2026-08-02 | 2026-08-09 | 2026-08-02 | 2026-08-09 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 06
| Validation by SE - Upstream | 5 | 2026-08-11 | 2026-08-16 | 2026-08-11 | 2026-08-16 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 06
| E2E - Upstream | 5 | 2026-08-23 | 2026-08-27 | 2026-08-23 | 2026-08-27 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 06
| E2E Comments Rectification - Upstream | 2 | 2026-08-30 | 2026-08-31 | 2026-08-30 | 2026-08-31 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 06
| Cuttover - Upstream | 1 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31 |  |  |  | Not Started | [9 empty] | Cutover | Batch 06
| - Upstream | [19 empty] | Batch 07
7th Batch (15 SS) | SLD and DB - Upstream | 7 | 2026-08-10 | 2026-08-17 | 2026-08-10 | 2026-08-17 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 07
| Validation by SE - Upstream | 5 | 2026-08-18 | 2026-08-23 | 2026-08-18 | 2026-08-23 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 07
| E2E - Upstream | 5 | 2026-08-30 | 2026-09-03 | 2026-08-30 | 2026-09-03 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 07
| E2E Comments Rectification - Upstream | 2 | 2026-09-06 | 2026-09-07 | 2026-09-06 | 2026-09-07 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 07
| Cuttover - Upstream | 1 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 |  |  |  | Not Started | [9 empty] | Cutover | Batch 07
| - Upstream | [19 empty] | Batch 08
8th Batch (15 SS) | SLD and DB - Upstream | 7 | 2026-08-18 | 2026-08-25 | 2026-08-18 | 2026-08-25 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 08
| Validation by SE - Upstream | 5 | 2026-08-26 | 2026-08-31 | 2026-08-26 | 2026-08-31 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 08
| E2E - Upstream | 5 | 2026-09-06 | 2026-09-10 | 2026-09-06 | 2026-09-10 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 08
| E2E Comments Rectification - Upstream | 2 | 2026-09-13 | 2026-09-14 | 2026-09-13 | 2026-09-14 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 08
| Cuttover - Upstream | 1 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 |  |  |  | Not Started | [9 empty] | Cutover | Batch 08
| - Upstream | [19 empty] | Batch 09
9th Batch (15 SS) | SLD and DB - Upstream | 7 | 2026-08-26 | 2026-09-02 | 2026-08-26 | 2026-09-02 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 09
| Validation by SE - Upstream | 5 | 2026-09-03 | 2026-09-08 | 2026-09-03 | 2026-09-08 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 09
| E2E - Upstream | 5 | 2026-09-13 | 2026-09-17 | 2026-09-13 | 2026-09-17 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 09
| E2E Comments Rectification - Upstream | 2 | 2026-09-20 | 2026-09-21 | 2026-09-20 | 2026-09-21 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 09
| Cuttover - Upstream | 1 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-21 |  |  |  | Not Started | [9 empty] | Cutover | Batch 09
| - Upstream | [19 empty] | Batch 10
10th Batch (15 SS) | SLD and DB - Upstream | 7 | 2026-09-03 | 2026-09-10 | 2026-09-03 | 2026-09-10 |  |  |  | Not Started | [9 empty] | SLD Submission | Batch 10
| Validation by SE - Upstream | 5 | 2026-09-12 | 2026-09-16 | 2026-09-12 | 2026-09-16 |  |  |  | Not Started | [9 empty] | SLD Validation | Batch 10
| E2E - Upstream | 4 | 2026-09-20 | 2026-09-24 | 2026-09-20 | 2026-09-24 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness Cutover Depend on Succesful Completion of E2E |  | E2E for Grid SS | Batch 10
| E2E Comments Rectification - Upstream | 2 | 2026-09-27 | 2026-09-28 | 2026-09-27 | 2026-09-28 |  |  |  | Not Started | [7 empty] | Handle grid models, graphics, data accuracy issues, not including field equipment and communication etc |  | E2E Rectification | Batch 10
| Cuttover - Upstream | 1 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 |  |  |  | Not Started | [9 empty] | Cutover | Batch 10
Migration | Alarm & Reporting Migration | 18 | 2026-07-20 | 2026-08-09 | 2026-07-20 | 2026-08-09 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability *Software Completion
| UI & Display Configuration | 18 | 2026-07-20 | 2026-08-09 | 2026-07-20 | 2026-08-09 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Workstation Availability
| Historian Migration | 65 | 2026-07-20 | 2026-10-03 | 2026-07-20 | 2026-10-03 |  |  |  | Not Started | [7 empty] | Depend on : *1st Round of Database Migration *Data Structure & Analysis from SE
Integration | DNMC Integration | 26 | 2026-09-29 | 2026-10-28 | 2026-09-29 | 2026-10-28 | [11 empty] | 1.Depend on DNMC is Completed 2.DNMC datapoint Scope 3.DNMC <-----> DCC telecom completed 4.ICCP Configuration 5.Testing（SDCC & DNMC ICCP Channel Testing） 6.Batch 10 Cut Over Estimate add 5 days to do DNMC ICCP Intergration 7.Estimate all step Completed on 8th Sep
| Local ESB Installation | 7 | 2026-06-30 | 2026-07-07 | 2026-06-30 | 2026-07-07
| Central ESB Integration（Third Partly System Phase 1） | 167 | 2026-06-21 | 2026-12-31 | 2026-06-21 | 2026-12-31 | [11 empty] | Details need be confirmed by SE and C-ESB side,under discussion. The relevant timeline can only be estimated as the following dependencies remain unconfirmed. 1.DEV timeline not be confirmed 2.Business flow not be confirmed between ADMS and TPS. 3.Interface not confimed because of the business flow. 4. Telecom condition timeline not be confirmed. 5.Detailed planned dates can not be clarified before the confirmation of the Change Order. 6.C-ESB hardware condition not be confirmed
| Central ESB Integration（Third Partly System Phase 2） | 129 | 2027-01-02 | 2027-05-31 | 2027-01-02 | 2027-05-31 | [11 empty] | Details need be confirmed by SE and C-ESB side,under discussion. The relevant timeline can only be estimated as the following dependencies remain unconfirmed. 1.DEV timeline not be confirmed 2.Business flow not be confirmed between ADMS and TPS. 3.Interface not confimed because of the business flow. 4. Telecom condition timeline not be confirmed. 5.Detailed planned dates can not be clarified before the confirmation of the Change Order. 6.C-ESB hardware condition not be confirmed
| DC-DR SYNC | 18 | 2026-12-01 | 2026-12-21 | 2026-12-01 | 2026-12-21 | [11 empty] | Depend on DC<---->DR Telecom Completed
Cut Over - Upstream (Live-On) | Cut Over（Batch1-10） | 3 | 2026-10-05 | 2026-10-07 | 2026-10-05 | 2026-10-07 |  |  |  | Not Started | [7 empty] | 1.Completed Cut Over(Upstream Batch1-10) 2.Completed SAT 3.Completed System Available Testing
ADMS SAT | Hardware cybersecurity test | 3 | 2026-09-17 | 2026-09-21 | 2026-09-17 | 2026-09-21 |  |  |  | Not Started
| Functional test | 4 | 2026-09-22 | 2026-09-28 | 2026-09-22 | 2026-09-28 |  |  |  | Not Started
| Redundancy test | 2 | 2026-09-29 | 2026-09-30 | 2026-09-29 | 2026-09-30 |  |  |  | Not Started
| Stability & unstructure test | 1 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2026-10-01 |  |  |  | Not Started
| Regression test | 1 | 2026-10-04 | 2026-10-04 | 2026-10-04 | 2026-10-04 |  |  |  | Not Started
Training | Training inside KSA | 30 | 2026-08-01 | 2026-09-10 | 2026-08-01 | 2026-09-10 |  |  |  | Not Started
| Training in Factory | 30 | 2026-10-14 | 2026-11-24 | 2026-10-14 | 2026-11-24 |  |  |  | Not Started
DERMS | DERMS Software Installation | 18 | 2026-09-05 | 2026-09-26 | 2026-07-20 | 2026-08-10 |  |  |  | Not Started | [7 empty] | The firewall configuration and required access rules shall be fully implemented and verified. Network access between the relevant systems and sites shall be available and confirmed. Connectivity between DC/DR shall be completed to support DC/DR communication and failover testing. All required ports, routing rules, and security policies shall be provided before testing.
| DERMS SAT | 11 | 2026-12-17 | 2026-12-31 | 2026-08-11 | 2026-08-25 |  |  |  | Not Started | [7 empty] | 1.Data for DER is required from SE
Dowstream | SLD and DB ( Total 3,500) | 91 | 2026-09-29 | 2027-01-12 | 2026-09-29 | 2027-01-12 |  |  |  | Not Started
| Validation by SE | 91 | 2026-10-15 | 2027-01-28 | 2026-10-15 | 2027-01-28 |  |  |  | Not Started | [7 empty] | 3 days FF with SLD 1st patch
| E2E for SFD (10% - 1400) | 66 | 2026-10-22 | 2027-01-21 | 2026-10-22 | 2027-01-21 |  |  |  | Not Started | [7 empty] | Depend on Telecom Readiness
| Cuttover | 1 | 2027-01-23 | 2027-01-23 | 2027-01-23 | 2027-01-23 |  |  |  | Not Started
Dowstream SAT | Functional test - ADMS | 4 | 2027-01-09 | 2027-01-13 | 2027-01-09 | 2027-01-13 |  |  |  | Not Started
| Integration test | 2 | 2027-01-14 | 2027-01-17 | 2027-01-14 | 2027-01-17 |  |  |  | Not Started
| Redundancy test | 2 | 2027-01-18 | 2027-01-19 | 2027-01-18 | 2027-01-19 |  |  |  | Not Started
| Stability & unstructure test | 1 | 2027-01-20 | 2027-01-20 | 2027-01-20 | 2027-01-20 |  |  |  | Not Started
| Regression test | 1 | 2027-01-21 | 2027-01-21 | 2027-01-21 | 2027-01-21 |  |  |  | Not Started
| Performance test | 3 | 2027-01-24 | 2027-01-26 | 2027-01-24 | 2027-01-26 |  |  |  | Not Started
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26
Contract. TCC: 24-Jul-26

## Summary Dates Option 01 &02 (2) (hidden)
| Western Rejion - Upstream | [11 empty] | Southern Rejion -Upstream
| Upstream Milstones |  |  |  | Upstream Milstones |  |  |  | Upstream Milstones |  |  |  | Upstream Milstones |  |  |  | Upstream Milstones
| MADINAH |  |  |  | JEDDAH |  |  |  | MAKKAH |  |  |  | ABHA |  |  |  | JIZAN
| E2E & Cutover (Grid SS) (Option 01) |  | Cutover Option 02 (Live on) |  | E2E & Cutover (Grid SS) (Option 01) |  | Cutover Option 02 (Live on) |  | E2E & Cutover (Grid SS) (Option 01) |  | Cutover Option 02 (Live on) |  | E2E & Cutover (Grid SS) (Option 01) |  | Cutover Option 02 (Live on) |  | E2E & Cutover (Grid SS) (Option 01) |  | Cutover Option 02 (Live on)
| Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates | Planned Dates | Expected Dates
Batch 01 | 2026-07-16 | 2026-07-16 | 2026-09-15 | 2026-09-15 | 2026-07-26 | 2026-07-26 | 2026-10-25 | 2026-10-25 | 2026-07-29 | 2026-07-29 | 2026-10-07 | 2026-10-07 | 2026-07-20 | 2026-07-20 | 2026-09-15 | 2026-09-15 | 2026-07-26 | 2026-07-26 | 2026-09-15 | 2026-09-15
Batch 02 | 2026-07-21 | 2026-07-21 |  |  | 2026-08-02 | 2026-08-02 | 2026-09-10 | 2026-09-10 | 2026-08-03 | 2026-08-03 | 2026-09-10 | 2026-09-10 | 2026-07-26 | 2026-07-26 |  |  | 2026-07-28 | 2026-07-28
Batch 03 | 2026-07-29 | 2026-07-29 |  |  | 2026-08-11 | 2026-08-11 | 2026-09-07 | 2026-09-07 | 2026-08-10 | 2026-08-10 | 2026-09-07 | 2026-09-07 | 2026-08-02 | 2026-08-02 |  |  | 2026-08-04 | 2026-08-04
Batch 04 | 2026-08-02 | 2026-08-02 |  |  | 2026-08-20 | 2026-08-20 | 2026-10-15 | 2026-10-15 | 2026-08-17 | 2026-08-17 | 2026-10-15 | 2026-10-15 | 2026-08-10 | 2026-08-10 |  |  | 2026-08-10 | 2026-08-10
Batch 05 | 2026-08-06 | 2026-08-06 |  |  | 2026-08-31 | 2026-08-31 | 2026-10-04 | 2026-10-04 | 2026-08-24 | 2026-08-24 | 2026-10-04 | 2026-10-04 | 2026-08-18 | 2026-08-18 |  |  | 2026-08-16 | 2026-08-16
Batch 06 | 2026-08-12 | 2026-08-12 |  |  | 2026-09-10 | 2026-09-10 |  |  | 2026-08-31 | 2026-08-31 |  |  | 2026-08-25 | 2026-08-25 |  |  | 2026-08-20 | 2026-08-20
Batch 07 | 2026-08-18 | 2026-08-18 |  |  | 2026-09-20 | 2026-09-20 |  |  | 2026-09-07 | 2026-09-07 |  |  | 2026-09-01 | 2026-09-01 |  |  | 2026-08-26 | 2026-08-26
Batch 08 | 2026-08-24 | 2026-08-24 |  |  | 2026-09-29 | 2026-09-29 |  |  | 2026-09-14 | 2026-09-14 |  |  | 2026-09-08 | 2026-09-08 |  |  | 2026-09-03 | 2026-09-03
Batch 09 | 2026-08-30 | 2026-08-30 |  |  | 2026-10-08 | 2026-10-08 |  |  | 2026-09-21 | 2026-09-21
Batch 10 | 2026-09-03 | 2026-09-03 |  |  | 2026-10-20 | 2026-10-20 |  |  | 2026-09-28 | 2026-09-28